## Bldg C 12WLOA
# | MEETING AGENDA
A | MEETING DETAILS
| MEETING. |  |  | PRODUCTION
| WEEK NO. |  |  | 9
| SECTION |  |  | C
| DATE |  |  | 2026-02-25
| TIME |  |  | 10:30
| LOCATION |  |  | Building C : R005
| PURPOSE |  |  | - To support and protect the Production Plan - To strive for improved Production Plan stability and predictability.
| NEXT MEETING |  |  | 2026-03-04
B | STAKEHOLDERS | Org. | In Attendance | Name | Column1
| Project Manager (PM) | RPN | Yes | Lorenzo Barnini
| Construction Manager | RPN | Yes | Matteo Naldi
| Cost Control Manager | RPN | No | Jessica Donatelli
| Engineering Chief & Move Manager | RPN | Yes | Federica Brunone
| Arch Design Specialist | RPN | No | Chiara Re Depaolini
| Schedule Manager | RPN | Yes | Simone Conti
| Move Specialist / Doc Controller | RPN | No | Martina Maffioletti
| Electrical Engineer | RPN | Yes | Hacir Degirmencioglu
| Deputy Quality Manager | RPN | Yes | Leonardo Valentinotti
| HSE & Security Manager | RPN | Yes | MariaCristina Menozzi
| Architectural Manager | SHP | Yes | Zeynep Onen
| Chief Design and Construction | SHP | Yes | Neil Bradley
| Project Manager (PM) | SHP | Yes | Patrick Fowler
| MEP Manager | SHP | Yes | Cedric Kusendova
| Change Manager | SHP | Yes | Maryna Chernova
| Design Manager (DM) | SHP | Yes | Jean-Mathieu Ferre
| Senior Electrical Engineer | SHP | Yes | Kateryna Starykova
| Senior Electrical Engineer | SHP | No | Benoit Renault
| MEP Manager | SHP | Yes | Cedric Kusendova
| MEP Manager | SOMBP | Yes | Cedric Erard
| Architect | SOMBP | Yes | Lucille Treille de Grandsaigne
| Architect | SOMBP | Yes | Rosario Marino
| Quality Manager | SHP | Yes | Didier Dequatre
C1 | MEETING TOPIC | ACTION - INFO | STATUS | DESCRIPTION - INFORMATION LOG | ACTION REQUIRED | PRIORITY | DUE DATE | OWNER ORG. | OWNER NAME 1 | OWNER NAME 2 | DISCIPLINE | DATE LOGGED | DATE CLOSED | ESCALATE | Note | Row_PM | Notify_PM | Condition_PM | ROW | Email_Name_1 | Email_Name_2 | SECTION | Nonull
C_1 | HEALTH & SAFETY | [21 empty] | N
HSE | Fire closure between Bldg C and AC - Level 4 & 5 |  | CLOSED | Permenent FR glazed door instaled at level 4 and 5 are not closing properly | 07.01: RPN to repair the locks. | TOP | 2026-01-28 | RPN | Matteo Naldi | [7 empty] | - | -- | 39 | matteo.naldi@cmbcarpi.it |  | C1 | Y
[17 empty] | - | -- | 40 |  |  | C1 | N
C_2 | PRODUCTION | [21 empty] | N
GENERAL | SUBSTANTIAL COMPLETION | INFO | OPEN | 18.02: Substantial completion is pending availability of EGGTELSA manpower on site 04.03 | 25.02: Official S.C. 24.04 (no exclusion) 04.03: RPN to confirm which areas can be delivered on 24.04. | High | 2026-03-06 | RPN | Simone Conti | [7 empty] | - | -- | 42 | simone.conti@cmbcarpi.it |  | C1 | Y
GENERAL | SUBSTANTIAL COMPLETION | INFO | OPEN | 07.05: Program have been updated with new S.C 16.12 TIA to 16.12 due to VAR 576 C6 / PRESS BAR / COUNCIL CHAMBER - NCF 334 salle C6 (see details bellow) - NCF 367 fire enclosure (see details bellow) | 14.05: Complete the works by the end of July 05.11: RPN to update board | High | [10 empty] | - | -- | 43 |  |  | C1 | Y
GENERAL | PPC | INFO | OPEN | 60% | 22.10: Blocking topic: - Lack of resources (EGGTELSA LB2/ Council chamber) - EGGTELSA have 25# on site (C + B + S2) - 8 to 10 peoples missing - Electrical instalation at LB2 - EGL | Low | [10 empty] | - | -- | 44 |  |  | C1 | Y
GENERAL | POLICE DU FEU | INFO | OPEN | 21.01: Planed 14.04 |  | Medium | [10 empty] | - | -- | 45 |  |  | C1 | Y
GENERAL | WINDOWS - NCF 382 (A-AB-C) | ACTION | OPEN | 18.02: New quality topic has been issued concerning windows NCF 18.02: Powder coating is cracking. 24.02: NCF 382 has been raised +/- 40 windows afected. 25.02: Supplier visited site | 25.02: RPN to organize site inspection with Manufacturer. +/- 03.03. | TOP | 2026-02-27 | RPN / SHP | Davide Cirillo | Didier Dequatre | [6 empty] | - | -- | 46 | davide.cirillo@cmbcarpi.it | didier.dequatre@un.org | C1 | Y
DESIGN | Phase 6 dwg As build dwg | INFO | OPEN | 28.01: +/- 100 Phase 6 dwg with R&R status 16.02: As built dwg list has been submitted | 04/03: SHP to assess | Medium | 2026-03-13 | SHP / SHP | Donatella Rocca | Jean-Mathieu Ferre | [6 empty] | - | -- | 47 | donatella.rocca@un.org | jean.ferre@un.org | C1 | Y
GENERAL | TCI - Follow-Up | INFO | OPEN | 17.09: TCI pending RPN = 92 SOMBP = 0 SHP =1 |  | Low | 2025-06-03 | RPN | Martina Maffioletti | [7 empty] | - | -- | 48 | martina.maffioletti@rpn-sa.ch |  | C1 | Y
GENERAL | EGGTELSA | ACTION | OPEN | EGGTELSA complains about 11 new INS / VAR impacting Substatial completion | 28.01: RPN to present a syntesis of issues and impact on delay | TOP | 2026-02-04 | RPN | Matteo Naldi | [7 empty] | - | -- | 49 | matteo.naldi@cmbcarpi.it |  | C1 | Y
GENERAL | FIRE MATRIX | INFO | OPEN | 03.12: meeting took place SBIS/ ENERGY MANAGEMENT 03.12: EGGTELSA needs 2month of works after Fire Matrix is approved 09.12: ENERGY MANAGEMENT provided info, pending SBIS 07.01: Fire Matrix have been uploaded on Pmweb, MEP approved as noted 14.01: Approved as noted (some doors missing) 17.02: FIRE MATRIX has been uploaded 21.02: phase.14 comments have been Uploaded. Status R&R (Minor comments, Technical issues are approved) | 21.01: RPN/ SBIS to update per comments 28.01: RPN to submit 11.02: RPN to submit on 11.02 18.02: SOMBP/ SHP to update 23.02: RPN to assess +/- 05.03 | TOP | 2026-03-05 | RPN | Federica Brunone | [7 empty] | - | -- | 50 | federica.brunone@cmbcarpi.it |  | C1 | Y
GENERAL | FIRE HOSES | ACTION | OPEN | 18.02: RPN instructed to PXT to reinstalled Fire hoses at Level 1 & 2 | 18.02: Fire hoses to be T&C + certified PXT to submit report | High | 2026-04-30 | RPN / RPN | Martina Maffioletti | Amos Anderini | [6 empty] | - | -- | 51 | martina.maffioletti@rpn-sa.ch | amos.anderini@rpn-sa.ch | C1 | Y
GENERAL | FIRE FIGHTER ROUTE - INS 421 - VAR 536 | ACTION | OPEN | 23.12: Step 4 has been submitted. 28.01: RPN planned completion of works by begining of march. | 21.01: RPN to plan execution in AC and S1 | High | 2026-02-08 | RPN | Matteo Naldi | [7 empty] | - | -- | 52 | matteo.naldi@cmbcarpi.it |  | C1 | Y
GENERAL | VIGANO - Wooden Doors - Windows frame - Furnitures | INFO | OPEN | 07.01: Windows frame to be completed by 19 of Jan 07.01: metal door to be delivered in January Acosutic doors in Febrary Wooden door delivery in March 21.01: VIGANO is back on site, window installation on going. EGGTELSA delayed by 1week 04.03: Doors delivery per VIGANO programme out of RPN control | 18.02: Priorities : - A.13 (high risk) - CAR @LB01 - Salle C6 interpretor booth (Acoustic test) - UNTV (Acoustic test) - Corridors @ L05-L04-L03... - Offices & other rooms @ L05-L04-L03... - Salon Tcheque, Council chamber | TOP | 2026-03-05 | RPN / RPN | Matteo Naldi | Lorenzo Barnini | [6 empty] | - | -- | 53 | matteo.naldi@cmbcarpi.it | lorenzo.barnini@cmbcarpi.it | C1 | Y
GENERAL | LIFTS - Planning | ACTION | OPEN | 02.10: INTERCOM to be GRANDSTREAM as approved on dwg. 26.11: EGL confirm T&C of lift 6 by end of February 07.01: EGL will be back on site 26.01. works to be completed mid of February. 04.03: RPN has been out of site for 2 weeks | 03.09: SHP to comment 10.09: RPN to submit platform dwg 24.09: Preparatory works to start 02.10 07.01: RPN to update planning | High | 2025-10-02 | RPN | Gianluca Crippa | [7 empty] | - | -- | 54 | gianluca.crippa@rpn-sa.ch |  | C1 | Y
LIFTS | LIFT 5, 6, 23, Platform C6, C5 | ACTION | OPEN | 17.12: Lift 6 strip out completed 14.01: instalation to start 26.01 26.01: MAS has been R&R | 28.01: Works started. Material for lift has been received. 11.02: RPN to check if Platform C5 is working | TOP | 2026-02-18 | RPN | Matteo Naldi | [7 empty] | - | -- | 55 | matteo.naldi@cmbcarpi.it |  | C1 | Y
EMERGENCY LIGHT | VAR 221 | ACTION | OPEN | 26.11: VAR was determined in summer 2024 Battery (Coffret Aprotec) have not been ordered (6 weeks lead time) No time impact will be accepted 19.01: EGGTELSA is anylising qty issues 04.02: RPN submitted comments 09.02: G&T submitted assessment | 04.02: G&T to assess 11.02: RPN to assess, 4 irelevant elements in balance. SHP to issue step 4 | TOP | 2026-02-11 | G&T | Clare O'Malley | [7 empty] | - | -- | 56 | c.omalley@gardiner.com |  | C1 | Y
FIRE CURTAINS | FIRE CURTAINS (8#) - OIBT | ACTION | OPEN | 26.11: Fire curtains (8#) are critical for OIBT (linked to UPS) 07.01: Fire curtains installation to start 12.01 14.01: Fire curtains have not been delivered 11.02: Installation started at salon tcheque 18.02: other Fire curtain to be delivered 02.03. 2 days of work per curtain x 2 teams 04.03: to arrvie 05.03 | 14.01: RPN to confirm delivery of fire curtains 21.01: RPN to confirm delivery of fire curtains 11.02: All curtain to be delivered 02.03 - RPN to confirm planning | High | 2026-01-28 | RPN / RPN | Matteo Naldi | Simone Conti | [6 empty] | - | -- | 57 | matteo.naldi@cmbcarpi.it | simone.conti@cmbcarpi.it | C1 | Y
L05-L03 | Displays in meeting rooms - VAR 478 | ACTION | OPEN | 25.02: IT works to be completed. 25.02: some TV to be delivered. 04.03: | 25.02: VAR 478 to be updated (TV size 65" = 75") 04.03: SHP to issue Revised step 4 - G&T to assess | High | 2026-03-06 | G&T | Clare O'Malley | [7 empty] | - | -- | 58 | c.omalley@gardiner.com |  | C1 | Y
L05 | WIFI | ACTION | OPEN | 30.09: Subcontractor is comming twice a year on site. mitigation action have been required following physical site survey. | 30.09: Based on predictive site survey status R&R. New simulation to be run. 10.11: RPN consultant to run physical survey together with ICTS and modify WAPS configuration on the spots until the physical survey is agreed. | High | 2025-10-10 | SHP / SHP | Dragos Ionescu | Jean-Mathieu Ferre | [6 empty] | - | -- | 59 | ionescud@un.org | jean.ferre@un.org | C1 | Y
L04 | MEETING ROOM L05 - VAR 659 - Obsolete luminaires | ACTION | OPEN | 25.02: MAS of new Luminaires to be approved 04.03: | 04.03: SOMBP/ SHP to assess is luminaire can be descoped 09.03: SOMBP to issue VAR to descope luminaire | High | 2026-02-26 | SOMBP | Cedric Erard | [7 empty] | - | -- | 60 | ce@erard.biz |  | C1 | Y
L01 | SALON TCHEQUE - Works | INFO | OPEN | 07.01: Existing panel can be maintained EGGTELSA is working in the BOH area 14.01: Fire curtains have not been received as planned. 04.02: Activities are longer than expected. 18.02: Fire curtains has been installed |  | TOP | 2026-02-10 | RPN | Matteo Naldi | [7 empty] | - | -- | 61 | matteo.naldi@cmbcarpi.it |  | C1 | Y
L01 | SALON TCHEQUE - Back door entrance @L02 | ACTION | OPEN | 23.02: Back door is an emergency exit. See VIGANO above |  | High | 2026-03-20 | RPN | Matteo Naldi | [7 empty] | - | -- | 62 | matteo.naldi@cmbcarpi.it |  | C1 | Y
L01 | SALON TCHEQUE - Temporary protection | INFO | OPEN | 28.01: All protection to furnitures ansd floor have been removed 24.02: Protection have been installed | 28.01: RPN to clean and protect | High | 2026-03-20 | RPN | Matteo Naldi | [7 empty] | - | -- | 63 | matteo.naldi@cmbcarpi.it |  | C1 | Y
L01 | SALON TCHEQUE - Relamping | ACTION | OPEN | 23.02: Light Tº are diferent (new and old) | 23.02: SHP to raise TCI | High | 2026-02-25 | SHP | Maximilien Montanaro | [7 empty] | - | -- | 64 | maximilien.montanaro@un.org |  | C1 | Y
L01 | SALON FRANCAIS - Wall mounted lighting | ACTION | OPEN | Check if wall mounted lights are in good conditions. 30.10: Assessment was partially made on site, 2 glass broken. | 30.09: Works to be assessed during site visit 03.11: Condition report to be checked, (=> NCF / INS?) Second assessment to be run | Medium | 2025-11-05 | SHP / RPN | Maximilien Montanaro | Matteo Naldi | [6 empty] | - | -- | 65 | maximilien.montanaro@un.org | matteo.naldi@cmbcarpi.it | C1 | Y
L01 | SALON FRANCAIS - Damaged carpet | ACTION | OPEN | 23.07: FLORENZ RAMSI will inspect on 07.08. 03.09: RPN received MOS from FLORENZ RAMSI 25.02: Carpet is back on site | 30.04: RPN to propose a solution for reparation. + liaise with heritage specialist 03.09: RPN to submit MOS 25.02: Carpet to be inspected | Low | 2026-03-05 | SHP / SHP | Maximilien Montanaro | Andrea Hoffman | [6 empty] | - | -- | 66 | maximilien.montanaro@un.org | ahoffmann@hoffmannart.ch | C1 | Y
L01 | SALLE 1 - Relamping | ACTION | OPEN | 21.01: Refer to MEP MoM. 28.01: recabling is ongoing. 28.01: 2 lamps went missing during the works (not produced any more) 18.02: MAS has been submitted (4000K) | 09.03: RPN to proceed | High | 2026-03-16 | RPN | Matteo Naldi | [7 empty] | - | -- | 67 | matteo.naldi@cmbcarpi.it |  | C1 | Y
L01 | SALLE 1 - NCF 380 Conditions AV equipment | ACTION | OPEN | 17.02: NCF 380 Salle 1 AV equipment conditions | 23.02: RPN to assess | Medium | 2026-02-25 | RPN / RPN | Davide Cirillo | Matteo Naldi | [6 empty] | - | -- | 68 | davide.cirillo@cmbcarpi.it | matteo.naldi@cmbcarpi.it | C1 | Y
L01 | COUNCIL CHAMBER - VAR 473 L02 SAS to council chamber | ACTION | OPEN | 03.10: SHP issued VAR Step 3 Rev 4 (painting of ceiling + emergency light product change) 15.10: RPN submitted updated cost proposal. 22.10: Ceiling have been removed, 1 ventilation duct have been found that do no comply with actual standard. SHP requested dwg to FMS. 29.10: SHP will not instruct RPN to duct the plenum | 22.10: SHP to assess 29.10: RPN to issue an RFI for formal confirmation | High | [10 empty] | - | -- | 69 |  |  | C1 | Y
L02 | SAS to COUNCIL CHAMBER - VAR 570 - LED to be integrated on the top of the frame | ACTION | OPEN | 22.10: RPN is reviewing with EGGTELSA. 10.11: Both SAS ceiling will be demolished (repainted in RAL), Walls to be repaired in false marble (D-PT-11). Doors with vision panels to receive D-PT-11 on coursive side, RAL 8008 on the SAS side. Handle and kick plate to be preserved. Oculus to be same size, centered. 28.01: All cost agreed 09.02: VAR step 1 has been issued 16.02: Step 3 has been issued | 09.02: RPN to issue step 2 23.02: RPN to issue commercial proposal | TOP | 2026-02-23 | RPN | Jessica Donatelli | [7 empty] | - | -- | 70 | jessica.donatelli@cmbcarpi.it |  | C1 | Y
L01 | COUNCIL CHAMBER - VAR 625 - Electrical panel F15 | INFO | OPEN | 14.01: AV issues to me moved to VAR 628 19.01: No issue on F15 panel due to AV equipments. 21.01: Panel will be delivered 10.02 28.01: Installation has not started. 1 month lost. 11.02: No blocking point. Missing manpower (agreement with RPN not found). Cabling to be completed before moving the tables (3P is blocked). | 25.02: Works ongoing 04.03: Final Inspection is planned for week 09.03 09.03: RPN to confirm readiness | High | 2026-03-06 | RPN / RPN | Hacir Degirmencioglu | Matteo Naldi | [6 empty] | - | -- | 71 | hacir.degirmencioglu@rpn-sa.ch | matteo.naldi@cmbcarpi.it | C1 | Y
L01 | COUNCIL CHAMBER - Interpretor booth | ACTION | OPEN | Perforation for new equipments to be confirmed on site Site visit has been runed | 30.09: Works to be assessed during site visit (26.11) 08.12: SHP to issue sketch, RPN to prepare mockup (with tape as in previous sections) 23.02: If few sockets are missing, RPN to submit daywork RFI | Medium | 2026-01-05 | RPN | Federica Brunone | [7 empty] | - | -- | 72 | federica.brunone@cmbcarpi.it |  | C1 | Y
L01 | COUNCIL CHAMBER - WINDOW MOTORIZATION | INFO | OPEN | 30.09: Upper windows have already been motorized. 19.11: delivery by mid january 28.01: Motors have been received 04.03: All motors have been installed. Upper part to be tested | 04.03: RPN to confirm installation | Low | 2026-02-13 | RPN | Matteo Naldi | [7 empty] | - | -- | 73 | matteo.naldi@cmbcarpi.it |  | C1 | Y
L01 | COUNCIL CHAMBER - TELEVIC inventory | INFO | OPEN | 17.11: RPN have submitted the TELEVIC inventory, 20251117_SOMBP_SMW_TA - OVERALL TELEVIC INVENTORY 16.01: Comments issued on Bluebeam | 19.01: SHP/SOMBP to share comments 19.01: RPN to rebuild spare parts inventory | Medium | 2026-02-02 | RPN | Federica Brunone | [7 empty] | - | -- | 74 | federica.brunone@cmbcarpi.it |  | C1 | Y
L01 | COUNCIL CHAMBER - CHAIRS VAR 40 | ACTION | OPEN | Some chairs to be repaired 28.01: Assessment have been done | 28.01: refurbishment is ongoing | Low | 2025-12-03 | RPN / SHP | Martina Maffioletti | Andrea Hoffman | [6 empty] | - | -- | 75 | martina.maffioletti@rpn-sa.ch | ahoffmann@hoffmannart.ch | C1 | Y
L01 | COUNCIL CHAMBER - Accessibility tables | INFO | OPEN | 15.12: tables to be modified for PMR 07.01: Table modification to be made on site 21.01: reposition by 16.02, adaptation by end of February 23.02: Works on going |  | Medium | 2025-12-03 | RPN / RPN | Martina Maffioletti | Matteo Naldi | [6 empty] | - | -- | 76 | martina.maffioletti@rpn-sa.ch | matteo.naldi@cmbcarpi.it | C1 | Y
L01 | COUNCIL CHAMBER - Temporary protection | INFO | OPEN | 28.01: All protection to furnitures ansd floor have been removed 18.02: Protection has not be reinstalled |  | Medium | 2025-12-03 | RPN |  | Matteo Naldi | [6 empty] | - | -- | 77 |  | matteo.naldi@cmbcarpi.it | C1 | Y
L01 | COUNCIL CHAMBER - VAR 399 Balustrade to coursive | ACTION | OPEN | 04.02: RPN propose solution C from the VAR. 09.02: Site visite is scheduled 10.02. 11.02: Handrail do not comply with SIA standard. | 04.02: RPN to confirm (refer to technical solution applied in Hall 14 mezzanine) 16.02: SOMBP to draft INS with improved design. 04.03: RPN subcontractor to assess about feasability | TOP | 2026-03-06 | RPN / SOMBP | Chiara Re Depaolini | Lucille Treille de Grandsaigne | [6 empty] | - | -- | 78 | chiara.redepaolini@rpn-sa.ch | lucille.treilledegrandsaigne@burckhardt.swiss | C1 | Y
L01 | COUNCIL CHAMBER - VAR 539 conference door | ACTION | OPEN | 04.03: VAR 539 step 3 Rev1 is under signature 06.03: Step 3 rev 1 has been issued 09.03: Access control is being installed on both side of the door | 23.02: SHP to update VAR 539 including Council chamber doors 0903: SHP to assess | High | 2026-03-20 | SHP | Maximilien Montanaro | [7 empty] | - | -- | 79 | maximilien.montanaro@un.org |  | C1 | Y
L01 | COUNCIL CHAMBER - LED Wall ventilation issue | ACTION | OPEN | 26.02: Casing as been supplied w/o required perforations. 04.03: Re-ordering the case may impact S.C. 04.03 COUNCIL CHAMBER is needed in June | 26.02: RPN to reject delivery/ submit manufacturer warranties | High | 2026-03-06 | RPN / RPN | Federica Brunone | Matteo Naldi | [6 empty] | - | -- | 80 | federica.brunone@cmbcarpi.it | matteo.naldi@cmbcarpi.it | C1 | Y
L01 | NCF 357 - AV cables quality | ACTION | OPEN |  | 24.11: RPN to comment | High | 2025-12-02 | RPN / SHP | Davide Cirillo | Patrick Vogelsang | [6 empty] | - | -- | 81 | davide.cirillo@cmbcarpi.it | patrick.vogelsang@un.org | C1 | Y
L01 | STAIR 6 LIGHTING | ACTION | OPEN | 17.12: installation +/- midle of march 21.01: Delivery by end of February/ begining of march 18.02: Lamps have been delivered, scaffold is under installation 23.02 Scafolds are in place 27.02: Wrong lighting has been sent | 04.03: RPN to issue updated MAS | Medium | 2026-01-29 | RPN | Hacir Degirmencioglu | [7 empty] | - | -- | 82 | hacir.degirmencioglu@rpn-sa.ch |  | C1 | Y
L00 | UNTV - Planning | INFO | OPEN | 14.01: Completion of the works by end of February 29.01: Move of equipement from Temporary to new studio: Monday 06.04 WHO/BIT start mid May. (Partial commissioning feasable before move) Move = 2 to 3 days, commissioning = +/- 1week. - 2 weeks move + commissioning - 3 weeks training - 1 week buffer 16.02: Gonogo meeting will take place on 02.04. 1st slot to swap UNTV studio is 07.04 < < 12.05 2nd slot is 13.07 < < Tbc | 26.01: RPN to update planning 18.02: T&C to proceed as planned | High | 2026-02-05 | RPN | Simone Conti | [7 empty] | - | -- | 83 | simone.conti@cmbcarpi.it |  | C1 | Y
L00 | UNTV - Security | ACTION | OPEN | 07.11: Sensitive equipment will be soon installed in the studio | 07.11: [Post 12WLA] RPN to enhance security in UNTV as soon equipment will be in place. 17.11: door to dock 5 has not been secured yet. | High | 2025-11-12 | RPN | Matteo Naldi | [7 empty] | - | -- | 84 | matteo.naldi@cmbcarpi.it |  | C1 | Y
L00 | UNTV - INS 544 Flash light + PA speaker - RFID 1489 | ACTION | OPEN | 19.11: Flash light / PA speaker missing in Studio 09.01: INS 544 has been submited by SOM 09.01: INS Issued 28.01: Scope is agreed but RPN price is outrageous | 4.02: RPN to revise cost (Engineering) 11.02: EGGTELSA to proceed | TOP | 2026-02-04 | RPN / RPN | Matteo Naldi | Jessica Donatelli | [6 empty] | - | -- | 85 | matteo.naldi@cmbcarpi.it | jessica.donatelli@cmbcarpi.it | C1 | Y
L00 | UNTV - Dust in CAR | ACTION | OPEN | 12.02: CAR | 16.02: NCF will be issued regarding dust in CAR | TOP | 2026-02-20 | RPN | Matteo Naldi | [7 empty] | - | -- | 86 | matteo.naldi@cmbcarpi.it |  | C1 | Y
L00 | AV display - VAR 490 | ACTION | OPEN | 04.02: SHP to update VAR 490 09.03: Issue with Marble on C6 entrance | 09.02: RPN to submit proposal (Concordia) SHP to revise VAR (2 displays in Bldg.C 46" => 55") 09.03: SHP to assess definitive position | High | 2026-02-27 | SHP / SHP | Maximilien Montanaro | Patrick Vogelsang | [6 empty] | - | -- | 87 | maximilien.montanaro@un.org | patrick.vogelsang@un.org | C1 | Y
L00 | PRESS BAR - MEDIA CENTER AREA C.2.3 - VAR 649, (INS 524), 6# Optical Fiber conection | ACTION | OPEN | 10.10: 8 additional BNC sockets to be installed in Press bar Lake side windows 07.11: [Post 12WLA Note] SHP issued draft INS. 10.11: INS have been issued. 25.11: UNIS have approved the proposal as per INS 524. 03.12: RPN submited step 2, VAR requested 21.01: VAR step 1 has been issued 26.01: Step 1 has been submitted 29.01: Step 3 has been issued 11.02: rack for 2 converters to be located boths side of entrance C23 18.02: CDP contract for the broadcast, dwg are required for the IT part | 16.02 RPN to issue commercial proposal 23.02: RPN to issue commercial proposal 04.03: RPN to assess TIA | High | 2026-02-02 | RPN / RPN | Jessica Donatelli | Federica Brunone | [6 empty] | - | -- | 88 | jessica.donatelli@cmbcarpi.it | federica.brunone@cmbcarpi.it | C1 | Y
L00 | PRESS BAR - INS 512 TC3-C4-2 storage (VAR Canceled) | ACTION | OPEN | 18.02: Newly build partition to be demolished | 18.02: SHP to review INS, | Medium | 2026-02-20 | SHP | Jean-Mathieu Ferre | [7 empty] | - | -- | 89 | jean.ferre@un.org |  | C1 | Y
L00 | PRESS BAR - Cingria mockup | ACTION | OPEN | 26.08: RPN to present a mockup (corner detail by VIGANO) + 1st installation as prototype 17.09: RPN to confirm 24.09: mock up to be presented 10.10. 22.10: RPN to confirm mock up presentation 14.01: RPN to confirm mock up presentation 18.02: no date provided by RPN | 28.01: Mockup is planned for the 9-10.02 18.02: SHP will request a visit to Vigano 25.02: Mockup to be presented 04.03. 09.03: Cingria is expected for Monday 16.03. | High | 2025-11-04 | RPN / RPN | Matteo Naldi | Chiara Re Depaolini | [6 empty] | - | -- | 90 | matteo.naldi@cmbcarpi.it | chiara.redepaolini@rpn-sa.ch | C1 | Y
L00 | PRESS BAR - Kitchen equipment | ACTION | OPEN | 01.10: Equipment to be delivered mid November 15.12: delivery of Kitchen equipment has been posponed BAR will be delivered at the last minutes 28.01: Installation of equipment have not started | 07.01: ceramic tiles under installation. Kitchen equipment instalation to start before end of Jan => 16.02 | Medium | 2025-11-15 | RPN | Matteo Naldi | [7 empty] | - | -- | 91 | matteo.naldi@cmbcarpi.it |  | C1 | Y
L00 | PRESS BAR - Furnitures | INFO | OPEN | 08.12: Enamelled CP tables to be restored (surface repair), heightened (leg extension?) + protective glass to be added on top 19.01: Dwg approved as noted |  | Medium | [10 empty] | - | -- | 92 |  |  | C1 | Y
L00 | PRESS BAR - Toilets | ACTION | OPEN | 01.10: Toilets have been completed with C status. | 01.10: RPN/ SOMBP to inspect | Medium | 2025-10-03 | RPN / SOMBP | Matteo Naldi | Lucille Treille de Grandsaigne | [6 empty] | - | -- | 93 | matteo.naldi@cmbcarpi.it | lucille.treilledegrandsaigne@burckhardt.swiss | C1 | Y
L00 | PRESS BAR - VAR 569 Water Fountain | ACTION | OPEN | 21.10: Step 4 has been issued 04.03: No water fountain to be installed |  | High | [10 empty] | - | -- | 94 |  |  | C1 | Y
L00 | UBS - Autorization to operate | INFO | OPEN | 08.05: UBS asked if they could officially be in the building right after Substantial completion | 08.05: SHP to confirm if UBS can start pperation after substantial completion | Low | 2025-05-30 | SHP | Didier Chessel | [7 empty] | - | -- | 95 | didier.chessel@un.org |  | C1 | Y
L00 | UBS - Remaining works | INFO | OPEN | 09.10: UBS to come back on site by the end of February 04.03: DI cables have been installed 04.03: PA cable will be pulled this week. | 09.10: SHP to confirm date when site condition will allow UBS to start completing works. | High | 2025-11-01 | RPN | Leonardo Valentinotti | [7 empty] | - | -- | 96 | leonardo.valentinotti@rpn-sa.ch |  | C1 | Y
L00 | UBS - Dedicated FIBER | ACTION | OPEN | 15.10: Federica email has been answered 10.11: UBS will have its own Fiber with dedicated provider (from T.17) 03.12: RPN is blocking the execution | 10.11: SHP/ RPN to check UBS IT dwg. In case unforeseen complication, alternative to be found. 03.12: RPN to clarify commercial position | Medium | 2025-11-01 | SHP | Jean-Mathieu Ferre | [7 empty] | - | -- | 97 | jean.ferre@un.org |  | C1 | Y
L00 | UBS - Automated windows | ACTION | OPEN | 25.11: UBS equiped with double flow ventilation. UBS required all windows to be locked. | 25.11: RPN to ensure windows can not be opened Windows are linked to smoke exhaust? | Medium | 2025-11-17 | RPN | Hacir Degirmencioglu | [7 empty] | - | -- | 98 | hacir.degirmencioglu@rpn-sa.ch |  | C1 | Y
L00 | INS 512 - TC3 storage partition | ACTION | OPEN | 11.02: INS has been canceled. 11.02: specialist to confirm potential normative issues if wall is not compliant. wall to be demolished. | 11.02: RPN to submit RFI if any normative issue | High | 2026-02-18 | RPN / RPN | Hacir Degirmencioglu | Matteo Naldi | [6 empty] | - | -- | 99 | hacir.degirmencioglu@rpn-sa.ch | matteo.naldi@cmbcarpi.it | C1 | Y
LB01 | SALLE C6 - Interpretor booth | ACTION | OPEN | 11.02: Vibrasto installation started 18.02: Ceiling to be completed next week | 18.02: Acoustic test to be launched as soon the doors have been installed | TOP | [10 empty] | - | -- | 100 |  |  | C1 | Y
LB01 | SALLE C6 - Furniture | ACTION | OPEN | 11.02: Furniture supplier to arrive begining of march | 25.02: Benchmark to be presented +/- 04.03. | Medium | 2026-03-04 | RPN | Matteo Naldi | [7 empty] | - | -- | 101 | matteo.naldi@cmbcarpi.it |  | C1 | Y
LB01 | SALLE C6 - Chinese donation delivery | ACTION | OPEN | 14.01: Shipment of lighting and mosaic is foreseen early feb. delivery mid-end of february | 14.01: RPN to schedule installation of lightings | High | 2026-03-01 | SHP | Jean-Mathieu Ferre | [7 empty] | - | -- | 102 | jean.ferre@un.org |  | C1 | Y
LB01 | SALLE C6 - Implementation of Chinese donation electrical devices | ACTION | OPEN | 04.03: SHP wonder that ELECTRICAL dwg have not been updated with chinese donation devices | 04.03: | [11 empty] | - | -- | 103 |  |  | C1 | Y
LB01 | SALLE C6 - Stretch Ceiling in staircase | ACTION | OPEN | 24.02: VAR 568 Salle C6 - access stair Emergency Lighting is on the way | 21.01: SHP to send an email to RPN confirming to go ahead with TD SHP to issue INS confirming new position of emergency light | High | 2026-02-18 | SHP | Jean-Mathieu Ferre | [7 empty] | - | -- | 104 | jean.ferre@un.org |  | C1 | Y
LB01 | Salle C6 - VAR 658 - Emergency light in staircase | ACTION | OPEN | 25.02: 3 additional Emergency lights have to be modified | 25.02: SHP to issue VAR 09.03: APROTEC to propose new model | High | 2026-03-11 | SHP | Kateryna Starykova | [7 empty] | - | -- | 105 | kateryna.starykova@un.org |  | C1 | Y
LB01 | Salle C6 - F. Brunome querries | ACTION | OPEN | 26.02: T23 / T13 sockets / RJ45 / KNX push buton. | 26.02: SHP to assess | High | 2026-03-06 | SHP / SHP | Cedric Kusendova | Patrick Vogelsang | [6 empty] | - | -- | 106 | cedric.kusendova@un.org | patrick.vogelsang@un.org | C1 | Y
LB01 | BMS - RFI 1421-C, panel TC.1.04 | ACTION | OPEN | 29.10: RFI 1421-A, B, C have been rejected | 29.10: RPN to submit RFI 1421-D | TOP | 2025-10-29 | RPN / SOMBP | Matteo Naldi | Cedric Erard | [6 empty] | - | -- | 107 | matteo.naldi@cmbcarpi.it | ce@erard.biz | C1 | Y
LB02 | BMS - Funccional Analisis - Wiring Diagram - Schematic | ACTION | OPEN | 08.10: Commercial issue Between Energie Management & RPN 22.10: Funccional analisis have been confidentially shared. 30.10: SHP submitted comments. 19.11: SHP commented dwgs 26.11: Johnson control ready to restart 03.12: Commercial issues with ENERGY MANAGEMENT have been solved. 03.12: RPN submitted functional analysis | 07.01: RPN to resubmit the wiring diagram | TOP | 2025-12-05 | RPN | Hacir Degirmencioglu | [7 empty] | - | -- | 108 | hacir.degirmencioglu@rpn-sa.ch |  | C1 | Y
LB02 | BMS - Planning | INFO | OPEN | 03.12: EGGTELSA face commercial issues with ENERGY MANAGEMENT Schematic will be submited in January => Bdg. C S.C., postponed to +/- June 10.12: EGGTELSA proceeding w/o ENERGY MANAGEMENT 07.01: EGGTELSA submitted planing => 15.09.26! 11.02: EGGTELSA has all documents in hand | 26.02: Works ongoing | TOP | 2025-12-05 | RPN / RPN | Simone Conti | Matteo Naldi | [6 empty] | - | -- | 109 | simone.conti@cmbcarpi.it | matteo.naldi@cmbcarpi.it | C1 | Y
LB02 | BMS PANELS - Procurement | INFO | OPEN | 03.12: [Lucille email] 5 are missing, including the most critical ones for ventilation and smoke extraction. 10.12: 1 Panel to be received in december, 4 panels in January 17.12: 1 Panel to be received in december, 1 panel begining of January, 2 panels in february, 1 panel by the begining of march. 17.12: Last panel (smoke exhaust) to be received by the end of March. |  | TOP | 2025-10-29 | RPN / RPN | Matteo Naldi | Lorenzo Barnini | [6 empty] | - | -- | 110 | matteo.naldi@cmbcarpi.it | lorenzo.barnini@cmbcarpi.it | C1 | Y
LB02 | Permanent Fire closure INS 541 | INFO | OPEN | 12.02: Inspection are ongoing | 12.02: RPN to involve SBIS in the inspections | High | 2026-02-19 | RPN / SBIS | Matteo Naldi | Olivier Zuercher | [6 empty] | - | -- | 111 | matteo.naldi@cmbcarpi.it | olivier.zuercher@sbis.ch | C1 | Y
LB02 | Temporary Fire closure INS 545 - RPN temp. High Voltage cable is on future escape route | ACTION | OPEN | 11.12: temporary Fire compartition required before SC 26.01: Step 1 has been issued 06.02: Step 2 has been issued. VAR is requested. | 12.02: as per Schedule 3 Chapter 17 – Business Continuity Part 3, Paragraph 3.1.C., | TOP | 2026-01-21 | RPN | Matteo Naldi | [7 empty] | - | -- | 112 | matteo.naldi@cmbcarpi.it |  | C1 | Y
LB02 | INS 543 - VAR 651 - SSS Village supply | ACTION | OPEN | 02.02: VAR has been sent on signature 11.02: dismantling of 2km cabling is urgent before ceiling will be closed | 04.03: G&T to assess | High | 2026-02-04 | G&T | Clare O'Malley | [7 empty] | - | -- | 113 | c.omalley@gardiner.com |  | C1 | Y
LB02 | ARCHIVES - VAR 659 - C009.1, 9.2, 9.3, 9.4 | ACTION | OPEN | 01.12: TD to be implemented in C-00-M9-1, C-00-M9-2, C-00-M9-3, C-00-M9-4 04.12: Remaining works: - Electrical works (Power, Cable trays, Smokes + fire detection, emergency lights, lights). => Works duration +/- 1 month 09.02: EGGTELSA 26.02: Second part of Archive to be inspected 04.03: Relamping to be discussed | 01.12: SHP/ RPN to review TD 04.12: RPN/ SHP to chalenge the design: - are all cable trays necessary? - can cables trays been relocated to position of easier installation? RPN to start begining of January 09.02: RPN to submit Value Engineering 26.02: SHP to liaise visit to LB2 / second part of archives (Ivan + Cedric + Hacir). 03.03: SOMBP/ SHP to assess, INS to be raised | TOP | 2026-03-06 | SOMBP / RPN | Cedric Erard | Hacir Degirmencioglu | [6 empty] | - | -- | 114 | ce@erard.biz | hacir.degirmencioglu@rpn-sa.ch | C1 | Y
LB02 | ARCHIVES MAG 10 - Floor finishes TCI |  |  |  | 19.01: SHP to raise TCI | High | 2026-01-23 | SHP / SHP | Zeynep Onen | Jean-Mathieu Ferre | [6 empty] | - | -- | 115 | zeynep.onen@un.org | jean.ferre@un.org | C1 | Y
LB02 | EVACUATION RAMP - Floor finishes TCI |  |  |  | 19.01: SHP to raise TCI | High | 2026-01-23 | SHP / SHP | Jean-Mathieu Ferre | Samuel Wilson | [6 empty] | - | -- | 116 | jean.ferre@un.org | samuel.wilson@un.org | C1 | Y
LB02 | ARCHIVES LB1-LB2-LB3 - VAR 581 Floor finishes | ACTION | OPEN | Linoleum is forcasted at level B3-B2-B1. It clashed with some doors 03.11: Step 1 issued on signature 26.01: Step 3 has been issued | 26.01: RPN to issue commercial proposal/ RPN to proceed with works | High | 2026-01-14 | RPN / RPN | Matteo Naldi | Jessica Donatelli | [6 empty] | - | -- | 117 | matteo.naldi@cmbcarpi.it | jessica.donatelli@cmbcarpi.it | C1 | Y
S1 - LB02 | BUILDING S1 LB02 - VAR 538 - Bldg S1 Basement Archive Security review | ACTION | OPEN | 26.01: Security / 2 doors / CCTV to be completed | 21.01: RPN to complete works. 28.01: RPN to confirm Wooden door delivery 04.02: RPN to issue commenrcial proposal | TOP | 2026-03-13 | RPN | Jessica Donatelli | [13 empty] | Y
S1 - LB02 | BUILDING S1 LB02 - VAR 557 - Bldg S1 - Minor security changes in Basement 2 | ACTION | OPEN | 05.11: Commercial proposal has been received and commented | 18.02: RPN to comment URGENTLY | TOP | 2026-03-13 | RPN | Jessica Donatelli | [7 empty] | - | -- | 119 | jessica.donatelli@cmbcarpi.it |  | C1 | Y
S1 - LB02 | BUILDING S1 LB02 - VAR 660 - Bldg S1 - Bulletproof partition | ACTION | OPEN |  | 04.03: SHP to raise VAR | TOP | 2026-03-13 | SHP | Jean-Mathieu Ferre
[17 empty] | - | -- | 122 |  |  | C1 | N
C_3 | TESTING & COMMISSIONING | [21 empty] | N
T&C | Phase 14 - Section of work | INFO | OPEN | 12.01: Handed over with C: - Bldg. S1 - LB1 (ready) - Bldg. D - LB1 (ready, VAR 488 trench to S2 will be handed over later) - Bldg. D - L00, handle to be changed on EI30 door - Bldg. D - L00 Entrance A.15 (linked to move from Palais Wilson) Handed over at a later stage: Bldg. S1 - LB2 => handed over with S2 Bldg. A - LB1 VAR 101 Bldg. A - LB1 Hervé workshop Bldg.A - LB1 & 2 corridor to CAF | 12.01: Eneor to reopen Bldg. S1 T&C | [11 empty] | - | -- | 124 |  |  | C1 | Y
| Annex leader |  |  |  | 12.01: SOMBP to confirm annex leader | [11 empty] | - | -- | 125 |  |  | C1 | Y
T&C - L05 | INSPECTION - MEP closure | INFO | CLOSED |  | 30.09: MEP fire closure to be checked | Low | [10 empty] | - | -- | 126 |  |  | C1 | Y
T&C - L05 | INSPECTION - Elec | INFO | CLOSED | 30.09: Final inspection ongoing on the corridor and external rooms Completion after window frame instalation 05.11: Activity will be completed by the end of december 18.02: RPN to rush completing L02 & L03 allowing Final Inspection to proceed | 11.02: SHP wil run pre-inspection visit on Thursday Friday to confirm works are ready for Final Inspections. | Low | [10 empty] | - | -- | 127 |  |  | C1 | Y
T&C - L05 | FAR | INFO | OPEN | 04.02: 30% of doors are not installed 11.02: No furniture in the print shop, neither in the pantry. +/- 60% of the area can be inspected 18.02: 50% of L05 FAR took 9h | 04.02: Intention is to perform partial architectural review / FAR. 11.02: SHP wil run pre-inspection visit on Thursday Friday to confirm works are ready for Final Inspections. 11.02: Pre-inspection to be run Monday 16.02 | Low | [10 empty] | - | -- | 128 |  |  | C1 | Y
T&C - Plan | T&C plan | ACTION | CLOSED | 03.09: T&C planning have been updated. Substantial completion by end of january. 17.09: RPN send Switch configuration IT room site visit planned 1st week of october | 20.08: RPN to submit T&C plan [Eneor] 10.09: RPN to submit PRIMAVERA schedule & protocols 02.10: RPN to organise a workshop +/- 15.10 | Low | [10 empty] | - | -- | 129 |  |  | C1 | Y
T&C - LB01 | IT Room - TCI_12109 Incorect optical fiber links |  |  | 11.11: TCI has been opened regarding recabling between C and S. |  | Medium | 2025-11-17 | RPN | Matteo Naldi | [7 empty] | - | -- | 130 | matteo.naldi@cmbcarpi.it |  | C1 | Y
T&C - L01 | FLUKE Test | INFO | OPEN | 30.09: FLUKE test will be mandatory |  | Medium | [10 empty] | - | -- | 131 |  |  | C1 | Y
T&C - L01 | COUNCIL CHAMBER - F15 Panel | INFO | OPEN | 16.10: turn on by mid January, prefunctional test begining of February Functional test mid February - early March 18.02: F15 pannel has been delivered | 11.02: Panel to be received this week. No consequence on Substantial Completion | High | [10 empty] | - | -- | 132 |  |  | C1 | Y
T&C | FIRE POLICE | INFO | OPEN | 16.10: end of march 26.11: begining of march | 16.10 RPN to identify Fire related test on the board | High | 2025-10-22 | RPN | Simone Conti | [7 empty] | - | -- | 133 | simone.conti@cmbcarpi.it |  | C1 | Y
T&C | AHU | ACTION | CLOSED | 16.10 Prefunctional test completed begining of january Completion for Mechanical Functional test mid january |  | Low | [10 empty] | - | -- | 134 |  |  | C1 | Y
T&C | LIFT 5, 6, 23, | INFO | OPEN | 16.10: Test to start begining of December | 16.10 RPN to build buffer on the keys topic | High | 2025-10-22 | RPN | Simone Conti | [7 empty] | - | -- | 135 | simone.conti@cmbcarpi.it |  | C1 | Y
T&C | OMM | INFO | OPEN | 16.10: 1 OMM to be submited prior to Substantial completion | 16.10: RPN to fix milestones & dead line | High | 2025-10-22 | RPN | Simone Conti | [7 empty] | - | -- | 136 | simone.conti@cmbcarpi.it |  | C1 | Y
T&C | PMP | INFO | OPEN | 16.10: 1 PMP to be submited prior to Substantial completion | 16.10: RPN to fix milestones & dead line | High | 2025-10-22 | RPN | Simone Conti | [7 empty] | - | -- | 137 | simone.conti@cmbcarpi.it |  | C1 | Y
T&C | TRAINING | INFO | OPEN | 16.10: 1 training to be submited prior to Substantial completion 16.10: +/- 2 to 3 weeks training sessions | 16.10: RPN to fix milestones & dead line | High | 2025-10-22 | RPN | Simone Conti | [7 empty] | - | -- | 138 | simone.conti@cmbcarpi.it |  | C1 | Y
T&C | AS BUILD | INFO | OPEN | 16.10: 1 Asbuild to be submited prior to Substantial completion |  | High | 2025-10-22 | RPN | Simone Conti | [7 empty] | - | -- | 139 | simone.conti@cmbcarpi.it |  | C1 | Y
T&C | UNTV | INFO | OPEN | 07.01: CAR to be completed mid January Edit & Control room to be completed end of january (consol & cabling) Studio to be completed en of February. PFP planned for end of February 21.01: T&C planning focus meeting to be organised 29.01 Final migration to be planned | 07.01: RPN to submit PFP ASAP | Medium |  |  |  | Abigail Abraham | [6 empty] | - | -- | 140 |  | donatella.rocca@un.org | C1 | Y
T&C | PMP submital | ACTION | OPEN | 07.01: ENERGY Management is working on it. 21.01; PMP will be submited by mid February 26.01: PMP, ENEOR to provide 80% of PMP based on phase 6 dwg within 09.02 | 26.01: RPN to ensure 80% of PMP are submited by 09.02. | High | 2026-02-09 | RPN | Leonardo Valentinotti | [7 empty] | - | -- | 141 | leonardo.valentinotti@rpn-sa.ch |  | C1 | Y
T&C | Training | ACTION | OPEN | Training, ENEOR sent email, | 26.01: ENEOR to confirm Training organisation | TOP | 2026-02-09 | RPN | Leonardo Valentinotti | [7 empty] | - | -- | 142 | leonardo.valentinotti@rpn-sa.ch |  | C1 | Y
FAR |  | ACTION | OPEN | 21.01: FAR will take +/- 2days per floor for Level 5-4-3 | 21.01: RPN / SHP to speedup Final inspection | High |  |  | Leonardo Valentinotti | [7 empty] | - | -- | 143 | leonardo.valentinotti@rpn-sa.ch |  | C1 | Y
[17 empty] | - | -- | 144 |  |  | C1 | N
[17 empty] | - | -- | 145 |  |  | C1 | N
C_4 | NCF | [21 empty] | N
NCF 379 | RADIATOR - Final inspection NCF 379 and Functional test | ACTION | OPEN | 04.02: remedial works can not been achieved before begining of may. FAR will not be achieved before all remedials works have been completed 25.02: FT completed | 04.02: Final inspection and Functional test to be performed as scheduled | High | 2026-02-11 | RPN / RPN | Leonardo Valentinotti | Matteo Naldi | [6 empty] | - | -- | 147 | leonardo.valentinotti@rpn-sa.ch | matteo.naldi@cmbcarpi.it | C1 | Y
NCF 367 | FIRE ENCLOSURE - VAR 644 - NCF 367 (general NCF) INS 518 | ACTION | OPEN | 22.10: gap between existig FR wall and slab to be sealed 29.10: general agreement - Holes < 5mm do not requires FR sealing - Holes drilled by RPN to be closed - Unexpected situation 10.12: Fire closure will be performed in January 26.01: Works ongoing 04.02: Completed for level 5-4-3 Level 2 Council chambe to be treated 25.02: Level 1 is ongoing | 26.01: 2 more issue on level 1, RPN to confirm 04.02: RPN to ensure SBIS participate to site visite 25.02: Final visit to be organised +/- 9.03 04.03: RPN to confirm SBIS availability for next week test | High | 2026-02-03 | RPN / SBIS | Matteo Naldi | Olivier Zuercher | [6 empty] | - | -- | 148 | matteo.naldi@cmbcarpi.it | olivier.zuercher@sbis.ch | C1 | Y
NCF 382 | WINDOWS | ACTION | OPEN | 04.03: CIMAN will visite the site on 04.03 | 04.03: RPN to assess the situation following manufacturer site visit. | High | 2026-02-03 | RPN / SHP | Davide Cirillo | Didier Dequatre | [6 empty] | - | -- | 149 | davide.cirillo@cmbcarpi.it | didier.dequatre@un.org | C1 | Y
NCF 383 | TRAVERTINE WALL COVERING | ACTION | OPEN |  | 04.03: SOMBP to raise | High | 2026-02-03 | SOMBP | Lucille Treille de Grandsaigne | [7 empty] | - | -- | 150 | lucille.treilledegrandsaigne@burckhardt.swiss |  | C1 | Y
[17 empty] | - | -- | 151 |  |  | C1 | N
C_5 | Bldg.C BLOCKING POINT | [15 empty] | - | -- | 152 |  |  | C1 | N
| VARIATIONS | INFO | OPEN | 01.10: 60 completed 100 to be completed 20 under commercial negociation | [12 empty] | - | -- | 153 |  |  | C1 | Y
| DWG with R&R status | INFO | OPEN | 11% of dwg under R&R - AV - Council chamber - UNTV - Salle C6 | [12 empty] | - | -- | 154 |  |  | C1 | Y
| DWG to be issued | INFO | OPEN | 45 - 50 dwg to be submited BMS / Fire matrx / Platform C6 | [12 empty] | - | -- | 155 |  |  | C1 | Y
| PMP | INFO | OPEN |  | 01.10: | High | 2025-10-05 | RPN | Federica Brunone | [7 empty] | - | -- | 156 | federica.brunone@cmbcarpi.it |  | C1 | Y
| Comissioning plan | INFO | OPEN |  | 01.10: | High | 2025-10-05 | RPN | Simone Conti | [7 empty] | - | -- | 157 | simone.conti@cmbcarpi.it |  | C1 | Y
| Switch delivery | INFO | OPEN | 11.11: [Dragos] Pending the end of the works in BTR.C (no date foreseen). The switches are ready for the handover. | 01.10: needed by mid November | Low | 2025-10-15 | RPN / SHP | Simone Conti | Dragos Ionescu | [6 empty] | - | -- | 158 | simone.conti@cmbcarpi.it | ionescud@un.org | C1 | Y
| CHANGE MANAGEMENT | [15 empty] | - | -- | 159 |  |  | C1 | N
[17 empty] | - | -- | 160 |  |  | C1 | N
Note on E42: 15.01: Target SC moved from late October to mid November 2025. 12.02: Programme have been updated 30.04: Operational Readiness 16.03.2026 07.05: TIA related to VAR 576 has been rejected. 17.09: SHP commented ultimate planning with S/C by the end of January. => Substantial Completion in January is not achievable without active action on planning and resources. 05.11: Substantial completion by end of February
Note on E48: • Aligning accountability by assigning clear ownership for pending QC/QA actions in the minutes. • Formally escalate and document blocking situations • Verify the effectiveness of corrective actions • Expose stakeholders' compliance per contractual obligations 28.05: TCI Pending 148 04.06: TCI Pending 164 11.06: TCI Pending 148 18.06: TCI pending = 136 27.06: TCI pending = 102 09.07: TCI pending RPN = 92 SOMBP = 7 SHP = 1 16.07: TCI pending RPN = 89 SOMBP = 7 SHP = 1
Note on E53: 09.07: Priority on UNTV / Access control / Electrical opening / offices 23.07. 30.07: Production of doors is blocked due to RPN/ VIGANO commercial issue. 20.08: VIGANO will end production with Building A. MANGINI / BARAUS to handover. 08.10: WINDOW FRAME installation to start 20.10 finish 28.11. - Salle C6 Woden panel 10.11 - Salle C6 Furnitures & frames 24.11 - Pantries 24.11 - Metal doors +/- mid december - Wooden doors TBC 22.10: Wooden door to be delivered 08.12 05.11: Delivery program is confirmed except for Wooden doors. Metal doors delivery is planed for January, and Wooden doors for February. 26.11: delivery 15.11 03.12: 1 week delay on window installation 10.12: Window frame on going at level 3 17.12: Window frame to be completed by begining of Jan.
Note on F53: 09.07: RPN to confirm potential impact on Substantial completion. 20.08: RPN to confirm 1st delivery. submit dwg, MAS and samples.
Note on E54: 09.07: Procurement 2 months (including August) + installation 2 month + T&C. 30.07: SHP notify that delay on desing may impact Substantial completion. 10.09: Dwg appoved by SOMBP.
Note on E55: 30.09: EGL is taking measurment on site. Material to arrive on site +/- mid november Lift 6 (Full replacement): completion mid december Lift 5 (Full replacement): completion mid january Lift 23: Platform Salle C6 Platform C5 22.10: Lift 23 is stacked between 2 floors 22.10: Starting 27.10, EGL will start working.
Note on E56: 13.07.24 : VAR has been determined. 27.08.24: RPN submitt NoD. SHP to confirm if NoD is covered by ammendment 7.
Note on E61: 29.10: Preparatory works started 05.11: Completion of painting is expected for 12/11 19.11: finishes on going 26.11: Painting completed
Note on E71: 25.07: RPN/ EGGTELSA raised issue about the certification of the F15 electrical panel. 15.08: : Extent of the works is agreed and validated, refer to MMs of EL WTM 5.539 for details 25.08: Approved solution: F15—F15-2 : new cables F15-2—Lights : existing cables F15—flat cables : new Flat cables : kept Flat cables –sockets : new 17.09: Step 3 issued 08.10: Strip out started today 15.10: F15 Panel have been ordered, 16.10: delivery mid december, Press bar is afected 22.10: Strip out to be completed 25.10 29.10: Strip out completed, cable pulling started 29.10: Step 3 rev1 have been issued w/o AV comments. RPN will proceed with 107 AV cables. 01.11: SHP submitted AV comments 05.11: Cable tray is under instalation 12.11: technical discussion ongoing regarding cable tray 26.11: Works on hold waiting for Commercial agrement 03.12: Works to start begining of January (dwg to be approved before) 2 month to complete the job 17.12: SHP/RPN agree to start execution based on phase 5 dwg submited together with VAR 625
Note on E74: 12.03: 3P started the invemtory 02.04: Inventory have been completed. 09.04: Inventory have been submitted. 29.10: 3P original inventory was not properly done.
Note on E83: HR61 23.02-02.04 WHO 13.05-23.05 BIT 01.06-12.06 ? mid june OHCR 08.09
Note on E110: 02.10: 46 dwg, 22 on Pmwb 21: dwg ready (Energie Management - EGGTELSA payment) 1: Functional analysis 2: panel impacted by VAR 110 & 146 + new panel impaced by VAR xxx PROCUREMENT: 16 panels in total 1 missing (Procurement) 01.10: RPN to confirm instalation status. 02.10: RPN to confirm on site delivery 15.10: Majority of BMS panels have been delivered. 22.10: RPN to solve technical issue on TC201

## VARIATIONS
Variation # | Variation Name | Section | Administrative Status of the Variations (Agreed / Determined, Cancelled, In Progress, To be issued) | Critical
R-VAR-0017 | SECURITY REVOLVING DOORS AND LOCKDOWN (PMI 026-027) | ALL | Agreed / Detemined
R-VAR-0025 | POSTAL SMART LOCKERS (PMI 031) (SSet 344) | S1/C/AC/B | Agreed / Detemined
R-VAR-0031 | GLAZED PARTITIONS FIRE RESISTANCE (SSet 327) | ALL | Agreed / Detemined
R-VAR-0034 | DOOR UPDATE BUILDINGS AC, B, S (SSet 323) | ALL | Agreed / Detemined
R-VAR-0040 | RESTAURATION OF HERITAGE FURNITURE (prov sum release) | ALL | Agreed / Detemined
R-VAR-0051 | FIRE SUPPRESSION SYSTEM (prov sum adjustement) | ALL | Agreed / Detemined
R-VAR-0062 | REPLACEMENT OF ASCENDER BY AQUILON | ALL | Agreed / Detemined
R-VAR-0063 | AH Interpreter Booth Changes - Equipment | ALL | Agreed / Detemined
R-VAR-0072 | AV BC INFRASTR OPTIMISATION (PMI 030) | ALL | Agreed / Detemined
R-VAR-0077 | AV MODIFS FOR SECTION C | C | Agreed / Detemined
R-VAR-0084 | NEW GENERATION BADGE READERS | ALL | Agreed / Detemined
R-VAR-0089 | HVAC CHANGES SALLE C6, TV STUDIO AND ATTENUATORS | C | Agreed / Detemined
R-VAR-0097 | POTABILITY TEST | ALL | Agreed / Detemined
R-VAR-0103 | AV DN NETWORK AND ANTENNA | ALL | Agreed / Detemined
R-VAR-0115 | ADDITIONAL ELEC/ICT SOCKETS IN CONF ROOMS (other Sections) | A/AB/C | Agreed / Detemined
R-VAR-0123 | UNTV CEILING AMENDMENTS | C | Agreed / Detemined
R-VAR-0127 | ANTI-INTRUSION SYSTEM | B/E/S1/C | Agreed / Detemined
R-VAR-0129 | AB AC CEILING INTERPRETER BOOTHS CORRIDORS AND FOYER SALLE III | ALL | Agreed / Detemined
R-VAR-0137 | WINDOW OPENING LIMITERS | ALL | Agreed / Detemined
R-VAR-0140 | ADDITIONAL FIRE EXTINGUISHERS BLDG A AND AC | ALL | Agreed / Detemined
R-VAR-0146 | BLDG C MC6 NEW CAR LOAD | C | Agreed / Detemined
R-VAR-0167 | UPPER WINDOW MOTORIZATION | C | Agreed / Detemined
R-VAR-0168 | BLDG C - UNTV CAR COOLING | C | Agreed / Detemined
R-VAR-0170 | NEW DOOR FOR SALON TCHEQUE ET SLOVAQUE | C | Agreed / Detemined
R-VAR-0173 | OVERALL BROADCAST (BROADCAST, LIGHTING AND SERVICES INCLUDED) | B/C | Agreed / Detemined
R-VAR-0175 | RAINWATER DRAINAGE CAR PARK P3 | ALL | Agreed / Detemined
R-VAR-0193 | BLDG A/AB TOILET CEILING CHANGES | ALL | Agreed / Detemined
R-VAR-0205 | SALLE IV HEATING AND COOLING | C | Agreed / Detemined
R-VAR-0220 | BLDGS AB & C VOLT DROP | ALL | Agreed / Detemined
R-VAR-0221 | EMERGENCY SIGNAGE AND LIGHTING UPDATE C | C | Agreed / Detemined
R-VAR-0233 | EVACUATION PLANS DRAWINGS AND INSTALLATION | ALL | Agreed / Detemined
R-VAR-0236 | HALL C - ENTRANCE C6 MODIFICATIONS | C | Agreed / Detemined
R-VAR-0240 | NEW FIRE DOORS BLDG A, AB, AC, B, C, S1, S2 | ALL | Agreed / Detemined
R-VAR-0243 | FIRE DETECTION SKYLIGHTS BLDG B and C | C/B | Agreed / Detemined
R-VAR-0255 | ELECTRICAL SUPPLIES FOR SMOKE EXTRACTION INSTALLATIONS | A/C/B | Agreed / Detemined
R-VAR-0260 | BLDGS A / AB / C - INTERPRETER BOOTHS ACOUSTICS | A/AB/C | Agreed / Detemined
R-VAR-0261 | BLDGS A / AB / C - INTERPRETER BOOTHS INTERIOR FITOUT CHANGES | A/AB/C | Agreed / Detemined
R-VAR-0274 | BLDG C PANTRY RISER AND RADIATOR RELOCATION PANTRY C.107 | C | Agreed / Detemined
R-VAR-0292 | LIGHTNING PROTECTION MODIFICATIONS (CDP) | ALL | Delay
R-VAR-0294 | LOCKING SYSTEM FOR EXISTING DOORS ON ESCAPE ROUTES | ALL | Agreed / Detemined
R-VAR-0311 | BMS AFTERCARE SERVICES | ALL | To be issued
R-VAR-0313 | BMS SUPERVISION WITH NIAGARA TRIDIUM | ALL | Agreed / Detemined
R-VAR-0320 | MASTERKEY STRATEGY | S1/C | In Progress
R-VAR-0336 | BMS INTEGRATION OF DHW CIRCULATION PUMPS | ALL | Agreed / Detemined
R-VAR-0343 | PERIPHERAL DOORS ASSESSMENT | ALL | Agreed / Detemined
R-VAR-0355 | BLDG C BLDG C L00 PRESS BAR COFFER VENTILATION | C | Agreed / Detemined
R-VAR-0358 | INTEGRATION OF LOCAL ALARMS WITHIN CARD READERS | ALL | Agreed / Detemined
R-VAR-0371 | KNX INTEGRATION CONTROLLERS | ALL | Agreed / Detemined
R-VAR-0375 | ALL BLDGS - MULTICREDENTIAL READER | ALL | Agreed / Detemined
R-VAR-0384 | KNX BMS INTEGRATION | ALL | Agreed / Detemined
R-VAR-0385 | BLDG C CLEANER'S ROOMS | C | Agreed / Detemined
R-VAR-0387 | BLDG C BLIND AND MOTORIZED WINDOW BOXES | C | Agreed / Detemined
R-VAR-0395 | BLDG C - COUNCIL CHAMBER AV RACKS RELOCATION | C | Agreed / Detemined
R-VAR-0397 | BLDG C SENSITIVE ROOMS - SALON TCHEQUE ET SLOVAQUE | C | Agreed / Detemined
R-VAR-0399 | BLDG C L02 COUNCIL CHAMBER GALLERY EXIT | C | Agreed / Detemined
R-VAR-0405 | BLDG C - FLS UPDATES | C | Agreed / Detemined
R-VAR-0406 | 2ND HANDRAIL IN STAIRCASES | AB/AC/C/B | Agreed / Detemined
R-VAR-0408 | ENTRANCE POSTS WITH SAFEROUTE | B/C/D/S1/S2 | Agreed / Detemined
R-VAR-0416 | BLDG C EXISTING OPENINGS IN BASEMENTS | C | Agreed / Detemined
R-VAR-0417 | BLDG C COUNCIL CHAMBER HEATING COILS BMS | C | Agreed / Detemined
R-VAR-0448 | BLDGS B & C - FLS POWER SUPPLY CABLE SECTIONS | B/C | Agreed / Detemined
R-VAR-0449 | BLDG C SENSITIVE ROOMS - SALON RUSSE + LOBBY | C | Agreed / Detemined
R-VAR-0456 | BDLG C SENSITIVE ROOMS - COUNCIL CHAMBER | C | Agreed / Detemined
R-VAR-0457 | BDLG C SENSITIVE ROOMS - SALON FRANCAIS | C | Agreed / Detemined
R-VAR-0464 | C14-C15 cables for the network switches | ALL | Agreed / Detemined
R-VAR-0473 | BLDG C - L01 FIRE CURTAINS STRUCTURAL IMPACT | C | In Progress
R-VAR-0474 | BLDG C - ENTRANCE AND PRESS BAR NEW STONE LAYOUT | C | Agreed / Detemined
R-VAR-0478 | ​Descope of AV equipment installed in meeting Rooms (CDP???) | AB/AC/C/S | Agreed / Detemined
R-VAR-0490 | DIGITAL SIGNAGE | A/AB/AC/C/S1 | In Progress
R-VAR-0493 | BLDG C - UNTV DOORS | C | Agreed / Detemined
R-VAR-0499 | Installation of Pressure Regulating Valves | ALL | Agreed / Detemined
R-VAR-0502 | Patching changes | A/AB/B/C/S1/S2 | Agreed / Detemined
R-VAR-0503 | Room C6 new layout | C | In Progress
R-VAR-0506 | BDLG C ADDITIONAL FIRE DETECTION DEVICES (CDP) | C | Agreed / Detemined
R-VAR-0512 | Bldg C stair 5 corridors changes | C | Agreed / Detemined
R-VAR-0515 | BLDG C STAIR 6 LIGHTING | C | In Progress
R-VAR-0521 | PA SPEAKERS BLDG C ATRIUM (CDP) | C | Agreed / Detemined
R-VAR-0525 | ADDITIONAL REVOLVING DOORS A17, A18, C21 | AB/C | Delay
R-VAR-0529 | Braille in handrails | ALL | To be issued
R-VAR-0533 | Bins fixed furniture descope | All | To be issued
R-VAR-0535 | BLDG C - DOOR UPDATES | C | Delay
R-VAR-0536 | BLDG C - FIRE INDICATOR UPDATES | C | Delay
R-VAR-0539 | Bldg A / AB Conference doors new doors buttons | A / AB / AC / C | Delay
R-VAR-0540 | Bldg C RF1 materials on Stair 5 | C | Delay
R-VAR-0544 | Salle C6 Chinese donation | C | Delay
R-VAR-0549 | Descope of outside cameras | ALL | Delay
R-VAR-0553 | FIRE CURTAIN KEYS | A/AB/AC/C/B/S1/S2 | Agreed / Detemined
R-VAR-0569 | Bldg C replace bar roller shutter | C | Delay
R-VAR-0570 | Bldg C L02 Door Design Clarification | C | To be issued
R-VAR-0573 | BLDG C L00 DOCK 5 DOOR UPDATE | C | Agreed / Detemined
R-VAR-0575 | AV-TR move for Room 1 | C | In Progress
R-VAR-0576 | BLDG C - FLS EL AND MH UPDATE | C | Delay
R-VAR-0577 | BLDG C - SECURITY UPDATE | C | Agreed / Detemined
R-VAR-0579 | Bldg C L00 - C6 entrance update | C | Agreed / Detemined
R-VAR-0581 | Bldg C Descope of basement linoleum flooring (ARCHIVES LB1-LB2-LB3) | C | To be issued
R-VAR-0591 | Council Chamber corridor ceiling L2 | C | Delay
R-VAR-0597 | BLDG C SECURITY THERMAL CAMERA POWER SUPPL | C | Agreed / Detemined
R-VAR-0599 | DESCOPE OF SECOND FEED | A/AC/C/B | Delay
R-VAR-0600 | Bldg C restauration miroir Kasskoff | C | Delay
R-VAR-0604 | BLDG C PRESS BAR COUNTER TOP | C | Delay
R-VAR-0611 | BLDS A, AB, B & C WINDOW FRAMES | AB/B/C | To be issued | Critical
R-VAR-0612 | VAR 173 revision Overall Broadcast (broadcast, lighting and services included) | B/C | To be issued
R-VAR-0618 | Bldg C Salle 1 Emergency Lighting | C | Delay
R-VAR-0624 | Bldg C Electrical panel board F15/2 | C | To be issued
R-VAR-0625 | Bldg C Electrical panel board F15 and cabling replacing | C | In Progress
R-VAR-0628 | Council Chamber AV - to check if eligible | C | To be issued
R-VAR-0629 | Door C5 cafeteria logistic adjustment (Bldg E catering BC) | C | To be issued
R-VAR-0631 | BLDG C – L00 – Existing Windows Wooden Frame | C | To be issued

## Bldg C - UBS (hidden)
# | MEETING AGENDA
A | MEETING DETAILS
| MEETING. |  |  | PRODUCTION
| WEEK NO. |  |  | 28
| SECTION |  |  | C
| DATE |  |  | 2025-07-12
| TIME |  |  | 11:00
| LOCATION |  |  | Building C : C-300
| PURPOSE |  |  | - To support and protect the Production Plan - To strive for improved Production Plan stability and predictability.
| NEXT MEETING |  |  | 2025-07-19
B | STAKEHOLDERS | Org. | In Attendance | Name | Column1
| Senior Architect | SHP | Yes | Samuel Wilson
| Design Manager (DM) | SHP | Yes | Jean-Mathieu Ferre
| Security Site Construction Management | SHP | Yes | Cinzia Porracin
| Move Specialist / Doc Controller | RPN | No | Martina Maffioletti | Agathe
|  |  | No |  | Arnaud |  | ºº
|  |  | No |  | arnaud
No
No
No
No
No
C1 | MEETING TOPIC | ACTION - INFO | STATUS | DESCRIPTION - INFORMATION LOG | ACTION REQUIRED | PRIORITY | DUE DATE | OWNER ORG. | OWNER NAME 1 | OWNER NAME 2 | DISCIPLINE | DATE LOGGED | DATE CLOSED | ESCALATE | Note | Row_PM | Notify_PM | Condition_PM | ROW | Email_Name_1 | Email_Name_2 | SECTION | Nonull
C_1 | HEALTH & SAFETY | [15 empty] | - | - - | 26 |  |  | C1 | N
[17 empty] | - | -- | 27 |  |  | C1 | N
[17 empty] | - | -- | 28 |  |  | C1 | N
C_2 | PRODUCTION | [15 empty] | - | - - | 29 |  |  | C1 | N
| UBS start of finishing works | ACTION | OPEN | 12.07: By mid january, UBS to start finishes works by mid January. +/- 2 months |  | Medium | 2025-08-18 | [9 empty] | - | -- | 30 |  |  | C1 | Y
| UBS operation | ACTION | OPEN | 12.07: By 16.03.2026. Worth case 01.07.2026 |  | Medium | [10 empty] | - | -- | 31 |  |  | C1 | Y
| OPEN HOUSE |  |  | 12.07: Their will be an Open House day, UBS will not be invited |  | Medium | 2025-07-15 | RPN / RPN | Matteo Naldi | Simone Conti | [6 empty] | - | -- | 32 | matteo.naldi@cmbcarpi.it | simone.conti@cmbcarpi.it | C1 | N
| Next meeting |  |  | 12.07: Friday 26.09 |  | Medium | 2025-06-03 | RPN / SHP | Davide Cirillo | Didier Dequatre | [6 empty] | - | -- | 33 | davide.cirillo@cmbcarpi.it | didier.dequatre@un.org | C1 | N
[6 empty] | High | 2025-07-17 | RPN | Jessica Donatelli | [7 empty] | - | -- | 34 | jessica.donatelli@cmbcarpi.it |  | C1 | N
[6 empty] | High |  | RPN | Matteo Naldi | [7 empty] | - | -- | 35 | matteo.naldi@cmbcarpi.it |  | C1 | N
[17 empty] | - | -- | 36 |  |  | C1 | N
[17 empty] | - | -- | 37 |  |  | C1 | N
C_3 | ING & COMMISSIONING | [15 empty] | - | - - | 38 |  |  | C1 | N
[17 empty] | - | -- | 42 |  |  | C1 | N
[17 empty] | - | -- | 43 |  |  | C1 | N
[17 empty] | - | -- | 44 |  |  | C1 | N
[17 empty] | - | -- | 45 |  |  | C1 | N
C_5 | DESIGN | [15 empty] | - | - - | 46 |  |  | C1 | N
[17 empty] | - | -- | 47 |  |  | C1 | N
[17 empty] | - | -- | 48 |  |  | C1 | N
[17 empty] | - | -- | 49 |  |  | C1 | N
[17 empty] | - | -- | 50 |  |  | C1 | N
[17 empty] | - | -- | 51 |  |  | C1 | N
CHANGE MANAGEMENT

## IT_Network_elevation
Prerequisites to handover the switches: |  | Action
1 | Rack elevations are approved in PMWeb;
2 | All works inside the TRs are finalized (except for the installation of the switches);
3 | The TRs are cleaned and dust free;
4 | If there are works generating dust in areas close to the TRs, the TRs have to be protected against the dust;
5 | The TRs’ doors have temporary locks (until the access control is activated).
Prerequisites to turn on the switches:
1 | All switches provided to RPN are installed according to the rack elevation provided by RPN;
2 | TRs are clean. The cleanliness has to be assessed by ICTS during a site visit.
3 | Keys of the TRs are provided to ICTS;
4 | The HVAC of the TRs is turned on;
5 | The protected electricity (UPS) is available in the racks;
6 | The certification of the optical fibers is approved in PMWeb;
7 | Optical fiber patch cables are provided to ICTS to connect the switches to the UNOG LAN;

## CLOSED
6 | CLOSED
C1 | MEETING TOPIC | ACTION - INFO | STATUS | DESCRIPTION - INFORMATION LOG | ACTION REQUIRED | PRIORITY | DUE DATE | OWNER ORG. | OWNER NAME 1 | OWNER NAME 2 | DISCIPLINE | DATE LOGGED | DATE CLOSED | ESCALATE | Note | Row_PM | Notify_PM | Condition_PM | Row | Email_Name_1 | Email_Name_2 | SECTION | Nonull
VAR 106 | BLDG C ARCHIVE FIRE PROTECTION |  | CLOSED | - |  | 0 | [6 empty] | 18.07.2024 |  |  |  |  | - | 118 | 0 | 0 | ActionClosed | N
VAR 138 | BLDG C - ARCHIVES VENTILATION - BASEMENT |  | CLOSED | C: 12/06/23 |  | 0 | [6 empty] | 18.07.2024 |  |  |  |  | - | 119 | 0 | 0 | ActionClosed | N
VAR 167 | UPPER WINDOW MOTORIZATION |  | CLOSED | - |  | INS 268, INS 326 | [6 empty] | 18.07.2024 |  |  |  |  | - | 120 | 0 | 0 | ActionClosed | N
VAR 180 | BDLG C LB2 PLANTROOM C.0014 |  | CLOSED | C: 28-Jul-23 |  | 0 | [6 empty] | 18.07.2024 |  |  |  |  | - | 121 | 0 | 0 | ActionClosed | N
VAR 221 | EMERGENCY SIGNAGE AND LIGHTING UPDATE C |  | CLOSED | No Info |  | INS 348 | [6 empty] | 2024-07-25 |  |  |  |  | - | 122 | 0 | 0 | ActionClosed | N
VAR 243 | FIRE DETECTION SKYLIGHTS BLDG B and C |  | CLOSED | - |  | 0 | [11 empty] | - | 123 | 0 | 0 | ActionClosed | N
VAR 249 | Bldg C- SKYLIGHT SECURITY AND LIGHTING CONTROL |  | CLOSED | - |  | 0 | [11 empty] | - | 124 | 0 | 0 | ActionClosed | N
VAR 260 | BLDGS A / AB / C - INTERPRETER BOOTHS ACOUSTICS |  | CLOSED | AB: 21/05/2024 C: 23/04/2024 |  | INS 311 | [11 empty] | - | 125 | 0 | 0 | ActionClosed | N
INS 341 | Bldg C fire dampers VAR 138 - Rev 1 |  | CLOSED | 0 |  | #N/A | [6 empty] | 18.07.2024 |  |  |  |  | - | 126 | 0 | 0 | ActionClosed | N
VAR 387 | BLDG C BLIND AND MOTORIZED WINDOW BOXES |  | CLOSED | - |  | 0 | [11 empty] | - | 127 |  | 0 | ActionClosed | N
VAR 395 | BLDG C - COUNCIL CHAMBER AV RACKS RELOCATION |  | CLOSED | C: 16-Apr-25 |  | 0 | [6 empty] | 2024-07-25 |  |  |  |  | - | 128 | 0 | 0 | ActionClosed | N
VAR 399 | BLDG C L02 COUNCIL CHAMBER GALLERY EXIT |  | CLOSED | - |  | 0 | [6 empty] | 18.07.2024 |  |  |  |  | - | 129 | 0 | 0 | ActionClosed | N
INS 408 | Bldg C - PA speakers L01-L02 - Open Aera Council Chamber - PA speakers |  | CLOSED | 0 |  | #N/A | [11 empty] | - | 130 | 0 | 0 | ActionClosed | N
VAR 416 | BLDG C EXISTING OPENINGS IN BASEMENTS |  | CLOSED | - |  | 0 | [6 empty] | 18.07.2024 |  |  |  |  | - | 131 | 0 | 0 | ActionClosed | N
VAR 426 | BLDG C - IT CABLING |  | CLOSED | - |  | 0 | [6 empty] | 18.07.2024 |  |  |  |  | - | 132 | 0 | 0 | ActionClosed | N
INS 409 | Bldg C stair 5 corridors changes |  | CLOSED | 0 |  | #N/A | [6 empty] | 2024-07-25 |  |  |  |  | - | 133 | 0 | 0 | ActionClosed | N
VAR 449 | BLDG C SENSITIVE ROOMS - SALON RUSSE + LOBBY |  | CLOSED | No Info |  | 0 | [11 empty] | - | 134 | 0 | 0 | ActionClosed | N
VAR 450 | BLDG C SENSITIVE ROOMS - SALLE 1 AND 2 |  | CLOSED | - |  | 0 | [5 empty] | 01.10.2024 | [5 empty] | - | 135 | 0 | 0 | ActionClosed | N
VAR 474 | BLDG C - ENTRANCE AND PRESS BAR NEW STONE LAYOUT |  | CLOSED | - |  | 0 | [6 empty] | 18.07.2024 |  |  |  |  | - | 136 | 0 | 0 | ActionClosed | N
VAR 493 | BLDG C - UNTV DOORS |  | CLOSED | - |  | 0 | [6 empty] | 6.11.2024 |  |  |  |  | - | 137 | neil.bradley@un.org | 0 | ActionClosed | N
VAR 494 | BLDG C - UNTV BLINDS |  | CLOSED | - |  | 0 | [6 empty] | 6.11.2024 |  |  |  |  | - | 138 | jessica.donatelli@cmbcarpi.it | 0 | ActionClosed | N
VAR 504 | Access control IT room LB1 S1 |  | CLOSED | No Info |  | 0 | [11 empty] | - | 139 | 0 | 0 | ActionClosed | N
VAR 506 | BDLG C ADDITIONAL FIRE DETECTION DEVICES (CDP) |  | CLOSED | No Info |  | 0 | [11 empty] | - | 140 | 0 | 0 | ActionClosed | N
| Final EL installation for Skylight RFI-0930-b |  | CLOSED | [9 empty] | 18.07.2024 |  |  |  |  | - | 141 | 0 | 0 | ActionClosed | N
| MAG 5.1 - MEP Installation blocked by archives presence |  | CLOSED | [9 empty] | 18.07.2024 |  |  |  |  | - | 142 | 0 | 0 | ActionClosed | N
| Opening for electrical elements to be validated |  | CLOSED | [9 empty] | 18.07.2024 |  |  |  |  | - | 143 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | VAR 527 has been issued | [12 empty] | - | 144 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | RPN subcontract to update documents | [12 empty] | - | 145 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | RPN to issue design | [12 empty] | - | 146 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | Subcontractor of roller shutter (Rieder) to provide missing technical informations (dimension & position of motor) | [12 empty] | - | 147 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | RPN to provide the List of equipment. To be confirmed by UNTV | [12 empty] | - | 148 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | Check with UNTV stakeholders whether vision panel in door type C_WD104 can be ommited | [6 empty] | 2024-07-07 | [5 empty] | - | 149 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | SOMBP to provide sketch | [6 empty] | 2024-08-06 | [5 empty] | - | 150 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | RPN to fill the gap with bricks, will be considered as exisiting | [6 empty] | 2024-08-06 | [5 empty] | - | 151 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | RPN confirmed the marble has been stored and will be reinstalled | [6 empty] | 2024-08-06 | [5 empty] | - | 152 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | 27.11 cost agreed, step 4 to be issued | 1 | [11 empty] | - | 153 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | 27.11 cost agreed, step 4 to be issued | 3 | [11 empty] | - | 154 | 0 | 0 | ActionClosed | N
|  |  | CLOSED |  | 27.11, cost agreed SHP to issue step 4 | TOP | [11 empty] | - | 155 | 0 | 0 | ActionClosed | N
| Planning updates | INFO (New) | CLOSED | 10.12: Visual board have been updated |  | Red | [7 empty] | Planning updates |  |  |  | Planning updates- | 156 | matteo.naldi@cmbcarpi.it | simone.conti@cmbcarpi.it | ActionClosed | Y
| SALLE 1 & 2 | INFO (New) | CLOSED | 03.12: EGGTELSA refuse the VAR 450 split (FLS updates) - VAR was determined on 19th of sept 2024. 11.12: EGGTELSA validated the cost and is proceeding |  | Red | [7 empty] | SALLE 1 & 2 |  |  |  | SALLE 1 & 2- | 157 | jessica.donatelli@cmbcarpi.it |  | ActionClosed | Y
| PRESS KITCHEN | INFO | CLOSED | Metal structure to support Chillers above cold room will be installed week 01.12 | [9 empty] | PRESS KITCHEN |  |  |  | PRESS KITCHEN- | 158 |  |  | ActionClosed | Y
| VAR 385 toilet | INFO | CLOSED | Works on going at leve 1 & 4 | [9 empty] | VAR 385 toilet |  |  |  | VAR 385 toilet- | 159 |  |  | ActionClosed | Y
| Revolving doors entrance C6 | INFO | CLOSED | 06.11: Dormakaba already came on site to take measurement of doors. Doors will be delivered +/- end of January | [13 empty] | - | 160 |  |  | ActionClosed | Y
| Insulation around Windows at level 5 | INFO (New) | CLOSED | 05.12: site visit, RPN raised an issue regarding colocation of insulating material around new windows that will damage the heritage marble in toilets | 11.12: SOMBP to assess whether insulation is required or can be omitted. 18.12: issue closed, see weekly Technical meeting #193 | [12 empty] | - | 161 |  |  | ActionClosed | Y
[18 empty] | - | 162 | 0 | 0 | ActionClosed | N
[18 empty] | - | 163 | 0 | 0 | ActionClosed | N
[18 empty] | - | 164 | 0 | 0 | ActionClosed | N
| RADIATOR PEDESTAL | ACTION | CLOSED | 12.02: sample have been approved 19.02: MAS have been submitted 26.02: MAS have been approved | -
| SALLE 1 - unexpected RJ45 | ACTION | CLOSED | 12.02: during Sensitive room site viste (11.02) unexpected new RJ45 in floor box was noticed 19.02: unexpected RJ45 is accepted as it is in floor box | 12.02: Sensitive room site viste notice unexpected new RJ45 in floor box. SHP to confirm if NCF/ TCI / RFI is to be raised
| TC5 | INFO | CLOSED | 10.02: 2 AV rack are to be removed from TC5 to perform activities | 18.02: SHP/ FMS will remove AV rack dedicated to salle 1. RPN/ 3P will remove AV rack deicated to Council chamber. 26.02: SHP/ FMS to remove AV rack dedicated to salle 1. | Medium
| UNTV - Works | INFO | CLOSED | [Records have been copied in commnents, refer to xls sheet for details] 19.02: Ecophon Ceiling haven't been installed and Electrical terminal haven't been installed in UNTV - does not affect Cleansite. |  | Low
| MEETING ROOM - AV | INFO | CLOSED | 12.02: VAR 299 show sound bar bellow TV. sockets are in conflict with the sokets. Overseen by VAR 478 19.03: INS received | 12.02: SMW (Ben Lang) to update VAR 299 including Roomba above TV. 19.02: SHP to clarify CISCOBAR and support detail | Medium
| SALLE C6 - Coordination | INFO | CLOSED | 19.02: Design includes AV conection and furniture in Mural 19.02: Position of cameras and speakers conflict with emergency signage | 19.02 Raise to architectural meeting | Medium
| UNTV - edit & Control room + touchdown | ACTION (New) | CLOSED | 12.03: False ceiling will be ready to install +/- 20.03 19.03: ELEC & Mechanical inspection have been run No Major issues | 26.03: RPN to issue MOM regarding last week site walks - cable tray mokeup - floor detail passage cables/ door | Medium
| PRESS BAR Cold room | INFO | CLOSED | 26.02: Cold room will be installed after all dusty works is completed |  | Low
| COUNCIL CHAMBER - Ceiling finishes | INFO | CLOSED | 02.04: no changes have been noted from the condition report. | 12.03: +/- 20m false marble ceiling @L0 and mezzanine to be repared. => RPN to propose cost | Low
| COUNCIL CHAMBER - Cameras | ACTION | CLOSED |  | 12.02 [AV focus meeting]: RPN to provide details of cameras for Historic architects approval. | Low
| UNTV - Colour of furnitures in Edit room | ACTION (New) | CLOSED | 26.03: SHP confirm that colour of furnitures in edit room is: STANDARD 7043 (dark grey) as per supplier's catalogue. | 26.03: RPN to order desks | Medium
| PRESS BAR INS 353 descope of shutter | ACTION | CLOSED |  |  | High
| SALLE 2 | INFO | CLOSED | [Records have been copied in commnents, refer to xls sheet for details] 12.03: Library is ready to move from Bldg. A to Bldg. C & AC 19.03: Hazard materious is preasent in flooring. Works will be proceed from bellow. RPN to inform SHP. | 26.03: RPN will raise RFI Daywork for ceiling restauration | Low
| UNTV - NCF | ACTION | CLOSED | 09.04: 2 NCF are open | 09.04: NCF were closed by dismantling the studio Administartive works to be completed | Medium
| UNTV - Contract for AV instalation | INFO | CLOSED | 09.04: Contract with VISUAL has been signed |  | TOP
| Door updates | ACTION (New) | CLOSED | 08.04: very urgent variation | 08.04: SHP to issue step 1 (on signature). | High
| ARCHIVES - MAG 6 | INFO | CLOSED | VAR 106 fire encasement of steel beams, only need paints 28.01 : UN Archive requires a plan to have this room back. 02.04: Pelichet is installing the shelves. 09.04: works completed, | 09.04: SHP to organise moves of the archives | Medium
| FLS design issues | INFO | CLOSED | 15.01: Leson learned from other sections to be implemented on site |  | Medium
| L0 | INFO | CLOSED | 05.02 Instalation of cable trays proceeding |  | Low
| L02 | INFO | CLOSED | 05.02 : Eggtelsa pooling cables | 19.03: Insulation behind radiator to be done | Low
| L03 | INFO | CLOSED | 19.02: Eggtelsa is proceeding | 19.03: Insulation behind radiator to be done | Low
| L04 | INFO | CLOSED | 22.01: ISOSUISSE to start ceiling installation 19.03: Insulation behind radiator has been done. |  | Low
| L05 | INFO | CLOSED | 22.01: Ceiling completed by ISO SUISSE first layer of painting completed. Carpet installed Linoleum to be installed at the last moment 19.03: Insulation behind radiator has been done. |  | Low
| COUNCIL CHAMBER - Fire curtains | INFO | CLOSED |  | 19.02: SHP to confirm architectural finishes 26.02: Consorcio Auro to propose matching color | Low
| COUNCIL CHAMBER | INFO | CLOSED | 22.01: 3P made a survey, all equipments are in place. Inventory to be submitted after Bldg. A & AB inventory is agreed. 19.02: Strip out started | 05.02: Preparatory work to start next week. 12.02: Strip out of old cables started (EGGTELSA) | Low
| Meeting room AV - INS 430 | ACTION | CLOSED | 02.04: RPN is requesting daywork | 02.04: SHP to issue step 3 | Medium
| SALON FRANCAIS - Leuleu table (shark skin) | ACTION | CLOSED | 09.04: Inspection has been run +/-1.5Y agor. Table is to be repaired 14.05: VIGANO is proceeding to refurbishment |  | Low
| UNTV - Rack elevation | ACTION | CLOSED | 13.05: Rack elevation design rev.6 has been submitted |  | TOP
| UNTV - Vapour barier | ACTION | CLOSED | 16.04: no MAS for the Installed Vapour Barier (yellow) has been approved nor submitted by RPN. installation no not comply with requirements. 30.05: Site adjustment will not affect clean site date. 14.05: ISOSUISSE is proceeding on site |  | Medium
| UNTV - INS 469 Window frame in Corridor | ACTION | CLOSED | 13.05: SOMBP issued INS 469 | 13.05: SHP to issue Step 1 | Medium
| UNTV - Doors & window supply | INFO | CLOSED | 19.02: Potential conflict between external windows and internal doors and "Clean site" 30.04: Windows have been received for LB01 and L00 Visual & Treepe site visit organized on 30.04 | 30.04: doors to be delivered.RPN to confirm 30.04: Visual & Treepe to start 05.05 | High
| All bldgs - Fire curtain keys VAR 553 | ACTION (New) | CLOSED | 21.05: | 19.03: RPN to issue commercial proposal | Medium
| SALON TCHEQUE - Zodiac Artwork | INFO | CLOSED | 16.04: Survey is ongoing Consorcio Auro do recomend comprehensive reparation | 16.04: SHP to raise the issue to Tcheque and Slovak delegation 07.05: SHP confirm that cracks will not be treated | Medium
VAR 600 | SALON FRANCAIS - Kasskoff artwork | ACTION | CLOSED | [Records have been copied in commnents, refer to xls sheet for details] 09.04: Gulia has provided feedback "Peeling is due to natural process". | 13.05: Cost has been approved. SHP to issue VAR | Medium
| SENSITIVE ROOM - Doors | ACTION (New) | CLOSED |  |  | High
| PRESS BAR - Fire closure in ceiling | ACTION | CLOSED |  | 14.05: [see rosario] RPN to share the schematic diagram of fire | Medium
| SALON FRANCAIS - VAR 457 | ACTION | CLOSED | [Records have been copied in commnents, refer to xls sheet for details] 02.03: VAR 457 Step3 rev. 1 has been issued |  | Medium
| ENTRANCE C6 - Fire panel | ACTION | CLOSED |  | 28.05: SHP to issue step 1
| PRESS BAR - Cingria substructure | ACTION | CLOSED | 28.05: EGGTELSA complete the works ISOSUISSE completeing the false ceiling
| SALON FRANCAIS - Emergency light in salon Roumain | ACTION | CLOSED | 30.04: Works to be done through Salle IV floor 04.06: path have been confirmed | 21.05: SHP to confirm the path | Low
F | SALLE C6 - Gap around Interpreter booth window - KNAUF diamond to be installed between Booth. | ACTION | CLOSED | 14.05: Discrepencies between approved design and execution 28.05: TCI was open and solution proposed. 06.04: NCF has been raised | 21.05: SOMBP to check with Kopitsis Lucille Treille de Grandsaigne (new email, UN-IT is working on the problem) | Medium
| SALLE C6 - Subwoofer | ACTION | CLOSED | 28.05: Subwoofer position is unique. | 14.05: Refer to AV meeting | High
INS 478 | SALON TCHEQUE - Lighting Fixtures | ACTION | CLOSED | 30.04: Outdated fluorescent light to be updated 15.05: RPN proposed LED lighting 10.06: INS 478 has been submitted |  | Low
| SALON FRANCAIS - Void | ACTION | CLOSED | 04.06: The void has been indentified as a ventilation plenum 11.06; confirmed
| PRESS BAR - Cingria prototype | ACTION | CLOSED | [Records have been copied in commnents, refer to xls sheet for details] 09.04: Survey has been runed. metal structure is required (big Cingria) Small cingria will be supported by inserts |  | Medium
| Works on Council chamber roof | INFO | CLOSED |  | 21.05: RPN will issue conditional report in DALUX 21.05: SHP to confirm load | Low
| Existing cupboard and internal doors | ACTION | CLOSED | 30.04: SHP/ SOMBP/ RPN have organized site survey ACAPI to start final painting by +/- 05.05. 14.05: RPN submit proposal - x% to RPN - x% fine - 1/3 to be shared - 1/3 to FMS 11.06: Damages are tracked by RPN RPN to paint the cupboard damaged by them only | 30.04: RPN to complete L02 & 03 and issue final site report 21.05 SHP to assess type of intervention (see ROSARIO email) 04.06: SHP/ SOMBP to assess and raise TCI | High
| SALON RUSSE - Furnitures | ACTION | CLOSED |  | 03.06: RPN to confirm that all furniture items included in the excel are in good condition and continue to work as intended. | Low
| SALLE 1 - Emergency light | ACTION | CLOSED | [Records have been copied in commnents, refer to xls sheet for details] 19.02: 1 Lux is required.SHP to confirm position 02.04: INS 454 emergency lights have bee received. 15.05: Step1 has been issued | 18.06: RPN to confirm if works can be covered by RFI daywork | Low
| WINDOW FRAMES - Plasterboard instead of wood | ACTION | CLOSED | [Records have been copied in commnents, refer to xls sheet for details] 30.05: SOMBP issued the INS 11.06: INS has been submitted 18.06: | 25.06: refer to Pre-Construction meeting | Medium
| SALON TCHEQUE - Sample painting | INFO | CLOSED | [Records have been copied in commnents, refer to xls sheet for details] 09.04: Sample painting has been done. 15.04: Colour samples have been presented & rejected. 28.05: New colours samples have been rejected. 27.06: sample colour has been approved "BLANC champigny mat" |  | Medium
| SENSITIVE ROOM - False ceiling finishes + SAS | INFO | CLOSED | 05.05: this VAR is in continuity of VAR 473 - fire curtains. 18.06: SOMBP sent revised step 3 25.06: revised step 3 issued |  | High
| COUNCIL CHAMBER - LED Wall | ACTION | CLOSED |  | 25.06: SHP to comment dwg. (TA + archi) | Medium
| COUNCIL CHAMBER - Slab | ACTION | CLOSED | 11.06: slab bellow platform is 1/2 cement 1/2 brick. | 11.06: RPN to propose an alternative solution to fix the LED wall. | High
| COUNCIL CHAMBER - Mezzanine corridor | ACTION | CLOSED | 04.06: Long part to be painted RAL laterral part to be repaint 11.06: G&T corrected the pirce | 04.06: depending on conditional report use shared risk allowance. | Medium
| COUNCIL CHAMBER - VAR 473 Fire curtain | INFO | CLOSED | 28.05: False ceiling has been dismanteled in vesitibule | 11.06: SOMBP to check cost file to align with Max request. | Low
| ROOF of S1 | INFO | CLOSED | 12.06: FMS informed SHP of the presence of construction material on the roof of Building S1- | 16.06: RPN to check if any material has been stored on the roof of Bldg. S1 | Medium
| IT Network Activation | ACTION | CLOSED | 12.07: Once prerequiste are full filled, Network can be activated in 1 week. | 12.07: IT room will be ready: - L2 & L4 end of July - LB01 end of August | Low
| IT NETWORK ACTIVATION | ACTION | CLOSED | 09.07: IT Network activation is planned for the 25.08 SHP+ ICTS inspection of IT room 4th & 5th floor ready by the end of July. ICTS to deliver switches + program. | 09.07: SHP to organise Technical launch meeting | High
| ARCHIVES - Smoke detectors Vs Shelves | ACTION | CLOSED | 21.05: SIEMENS made comments regarding the position of the smoke detector & shelves 18.06: VAR 576 to be revised 09.07: VAR 576 rev 1 have been issued | 09.07: RPN to issue step 2 | Medium
| SALLE 1 - Corridor Colour | ACTION | CLOSED | 29.04: INS 461 have been sent for signature 09.07: INS have been issued |  | High
| PLANNING - Stone Level 0 | ACTION | CLOSED | 09.07: Stone supplier changed for Level 0. New stone approved. - Delivery 2 month + August = end of September + 3 weeks installation - Impact on press bar furniture and glazed partitions, 16.07: In line with S/C |  | High
| fibers in room S.84 and S.63. | ACTION | CLOSED | 15.07: Fiber is required for UNTV BC | 15.07: RPN to confirm fibers have been already pulled. is S.76 included? | High
| Door modification markup | INFO | CLOSED |  | 03.06: RPN requires extra cleaning fees due to proximity with UNTV. Why? | Low
| Rack elevation | INFO | CLOSED | 04.08: Rack elevation have been approved | 12.07: RPN to request delivery of the swithes to Dragos (Guillermo Garcia) 30.07: SHP to comment Rack elevation rev.8 | Low
| SALON RUSSE | ACTION | CLOSED | 03.09: existing cables to be kept | 27.08: SHP to confirm if existing cables can remain or have to be changed. | Medium
| ARCHIVES - MAG 6 | INFO | CLOSED | Archives have been moved in | 01.06: Temporary door to be locked. Key to be provided to Library. RPN to ensure no construction works in this space dust afect stored archives | Low
| ARCHIVES LB1 - MAG 10.2 @ LB2 | INFO | CLOSED | Shelves are installed and empty | 06.08: completed | Low
| ARCHIVES - MAG 5.1 | INFO | CLOSED | Electrical installation to be completed + wall to be demolished 02.04. Final activities (EGGTELSA) to start 06.04 | 06.08: completed | Low
| ARCHIVES - Move | INFO | CLOSED |  | 30.04: moves to start +/- 05.05 | Low
| SALLE C6 - VAR 544 | ACTION | CLOSED | 3.12: doors colours to be confirmed urgently. 15.01: door color has been confirmed. 12.02: Raised floor is completed 16.04: VAR 544 draft have been issued 14.05: Stair area to be put on hold 21.05: Staircase has been frozen, will be confirmed at a latter stage | 09.07: RPN to submit step 2 | High
| SALLE 1 - EMERGENCY LIGHTING | ACTION | CLOSED | 01.09: VAR has been issued |  | Medium
|  | INFO | CLOSED |  | 23.07: Site visite on 24.07 to clarify scope of works. | Medium
| UNTV - Temporary storage | ACTION | CLOSED | 10.09: Insulation works on going. UNTV to move in by the end of September | 10.09: RPN to confirm completion of the works FMS to stop the heat circuit to allow relocation of radiator | TOP
| WINDOW FRAME - to be EI rated | ACTION | CLOSED | WINDOW FRAME - INS 461 / VAR 631 to be EI rated | 10.10: SOMBP to upload VAR 631 step 1 | Low
| COUNCIL CHAMBER - VAR 625 - AV circuit brakers | ACTION | CLOSED | 30.09: No new circuit brakers |  | Medium
| COUNCIL CHAMBER - VAR 625 - Panel F15 | ACTION | CLOSED | 30.09: SHP issued Step 3. | 30.09: RPN to confirm commercial offer | Medium
| SALON TCHEQUE - INS 478 - Lighting fixtures replacement | ACTION | CLOSED | Step 2 has beeen issued 30.07: INS 478 received, 01.09: RPN submitted a proposition | 17.09: SHP to comment RPN proposal | Medium
| LIFTS - Intercom | ACTION | CLOSED | Commend system for all lifts starting with C | 03.09: SHP/RPN to organise a workshop 01.10: Refer to Vertical Transportation meetings | High
| UNTV - Radiators | ACTION | CLOSED |  | 01.10: RPN to confirm details | Medium
| UNTV - Temporary door | ACTION | CLOSED | 01.10: Temporary dust proofd¡ door is required to guarantee AV equipment installation. | 01.10: RPN to install temporary dust proof doors to UNTV area | High
| UNTV - Move out from Bldg E | ACTION | CLOSED | 05.09: Urgent - RPN to coordinate with 3 P SMPTE 311 cables connection immediately. Starting 08.09 - Temporary UNTV studio in Bldg. A L07 will be operational. RPN to confirm control room 1 & 2 and edit room 1&2 readiness on 12.09 (as stated during 12 WLA). Starting 15.09 - UNTV shutdown in building E. - RPN to coordinate with Visuals to start installing equipment in CAR. 19.09: UNTV confirmed move out 15.10 | 03.09: SHP to confirm schedule of UNIS move out. 17.09: SHP to confirm schedule of UNIS move out. | Medium
| COUNCIL CHAMBER - VAR 6xx Operator booth junction box 15/2 | ACTION | CLOSED | 22.10: Junction box is included in TD |  | Low
| COUNCIL CHAMBER ADITIONAL CABLE TRAY - IT cables VS F15 cables | ACTION | CLOSED |  | 30.09: RPN to identify potential clashes between IT and small power cables | Low
| SALON FRANCAIS - Sockets | ACTION | CLOSED | 15.10: 4 Sockets are empty box, recabling is dificult 22.10: RPN + SOM agree to permanently seal those 4 sockets | 15.10: RPN to confirm feasability 22.10: SHP/ RPN to agree on covering plate | Medium
| SALON TCHEQUE - Door to Balcony | ACTION | CLOSED | 30.09: Dwg approved | 30.09: RPN to procure and install the door | Medium
| SAS to COUNCIL CHAMBER - 3 new doors | ACTION | CLOSED | 30.09: Dwg approved | 30.09: RPN to procure and install the door (VIGANO) | Medium
| RFI 1391 - Meeting room | ACTION | CLOSED | 30.09: Clash between installed sockets and required supports RFI has been rejected. | 30.09: Commercial review based on existing VAR 299, 478 and INS. RPN to reissue rejected RFI Daywork 1391 | TOP
| PRESS BAR - VAR 576 - Fire damper | ACTION | CLOSED | 24.09: Conflict have been detected 23.10 Fire dampers have been installed. |  | Medium
| VAR 576 - FLS updates | ACTION | CLOSED |  | 30.09: Fire evacuation plan dwg to be approved SHP to upload status on Pmweb | Medium
| UNTV - Temporary storage in S1 | ACTION | CLOSED | 01.10: | 01.10: RPN to check with SBIS for the use of the space RPN to raise Fiche d'intervention RPN to open temporary FR door | Medium
| UNTV - Clean Site Clarification | ACTION | CLOSED | 04.06: VIBRASTO is late +/- 2 weeks VISUAL to confirm impact on substantial completion 11.06: VISUALS confirm no impact expected on SC 27.08: VISUALS Stop working in CAR due to lack of space in cable trays. 17.09: VISUALS to start working after RFI 1439 A is closed 08.10: FAR AR for Control & Edit room planned 16.10 - Touch down & Studio to be checked later 15.10: Final check of touch down | 01.10: RPN/ SHP to focus on T&C 01.10: RPN to achieve clean site on 16.10 | Low
| COUNCIL CHAMBER - VAR 625 - Trenches | ACTION | CLOSED | 10.10: Site walks have been organised. 15.10: Target is to reduce the number of cables and avoid enlarging the trench 22.10: Assesment regarding IT and AV cables have been conducted 29.10: RPN confirmed the existing trench is fine |  | TOP
| PRESS BAR - Access hatches | ACTION | CLOSED |  | 01.10: RPN to require 2 additional access hatches | Medium
| PRESS BAR - VAR 576 - 3+1 fire dampers | ACTION | CLOSED | 29.10: Fire dampers have been installed | 01.10: RPN to install ASAP | Medium
| CAR - cleaning | ACTION | CLOSED |  |  | High
| UNTV - DMX RFI 1439-B | ACTION | CLOSED | 01.10: SHP comments issued today | 01.10: RPN to double check with OIBT controler (2 diferent sockets in the same box?) Cable tray to be installed underneath. Panel layout to be finalized. | Medium
| SALLE 1 - VAR 618 Emergency lighting | ACTION | CLOSED | 09.10: SHP issued comments, + Step 3 05.11: Step 2 issued, cost agreed | 05.11: SHP to issue step 4 | High
| Smoke extractor | INFO | CLOSED | 30.09: Smoke extarctor is in place |  | Low
| LIFT 23 - Business Continuity | ACTION | CLOSED | 13.10: actual lift is used by library Wenesday 10:00 to 12:00 05.11: Lift 23 is definitely turned of. |  | Low
| VIGANO VAR 611 - Window frame Level 05-04-03 | ACTION | CLOSED | 08.10: Refer to VIGANO 30.09: Completion 2.5 weeks/ level after delivery => Midle of december 15.10: Window frame to arrive 20.10. 29.10: instalation started at level 5 |  | Low
| WINDOWS | ACTION | CLOSED | 03.11: due to bad experience on Bldg. A, windows to be cauciously inspected |  | High
| UNIS - VAR 638 Additional Fire dampers | ACTION | CLOSED | 4 Fire dampers to be installed. | 29.10 SHP to issue VAR step 1 05.11: VAR Canceled, Fire dampers included in TD | High
| UNTV - Works | INFO | CLOSED | 23.07: Rails in studio to be installed in TV studio Cabling started in Edit room 22.10: Architectural review have been conducted. 29.10: VISUAL to start in Control and Edit room. | 03.11: SHP to assess RPN pictures | Low
| SALON FRANCAIS - VAR 600 KASSKOFF | INFO | CLOSED |  |  | Low
| DOOR C6 - Architectural dwg | ACTION | CLOSED |  | 28.10: SHP to comment dwg | High
| SALON TCHEQUE - RFID 1446 Lighting fixtures | ACTION | CLOSED | 22.10: RFI day work 1446 have been issued | 22.10: SHP to comment | Medium
| PANTRY & PRINT ROOM - Fixed furnitures delivery | ACTION | CLOSED | 08.10: Fixed furniture to be delivered by 24.11 |  | High
| UNTV - Chilled beam | ACTION | CLOSED |  | 01.10: Alignement to be checked | Medium
| COUNCIL CHAMBER - Interpretor booth heating | INFO | CLOSED | 22.10: as per MINERGIE requirements & SIA, existing heating coil should be updated. 17.11: No changes to be executed |  | Low
| TOILET Final inspection | ACTION | CLOSED |  | 30.09: RPN to invite for final inspection | Medium
| IT Room inspection | INFO | CLOSED | 17.09: Final Inspection of IT room L04-l02 BLDG C and FI IT installation VAR 239 BLDG S1 planned 01.10 Access control Test and Final Inspection follow up BLDG AB and FI IT room LB1 BLDG C planned 14-15.10 08.10: Installation is not in line with the overall design (but it works). 27.10: Final Inspection have been postponed to 30.10 01.11: Ceiling and wall to be finished, stair to be fixed. 10.11: Inspection failed 19.11: Inspection successful, Switches delivered.4 |  | High
| DOOR C6 - INS 477 Fire panel | ACTION | CLOSED | 01.10: RPN requested a VAR. refused by SHP. 26.11: EGGTELSA have 4-5 weeks lead time | 01.10: RPN to issue daywork RFI. | Medium
| SALLE C6 - Works | INFO | CLOSED | 28.05: Floor box have been cut 30.07: Production is wainting for design. 3P is working in Bldg AB. 29.10: LED wall installation to start this week 03.12: NCF 334 has been approved |  | TOP
| VAR 515: - Stair 6 lighting | INFO | CLOSED | 30.09: 12 weeks procurement on 10.11: VAR under signature 12.11: Delivery by January 03.12: MAS have been approved by SOMBP 08.12: MAS have been approved by SHP |  | Low
| CEILING | ACTION | CLOSED |  | 12.11: Ceiling details to be approved | Medium
| UBS - Opening ceremony | INFO | CLOSED | 08.05: In case an opening ceremony is organised (2-3 weeks before Operational readiness), UBS would like to be open that day. | 08.05: SHP to confirm if and when an opening ceremony will be organized | Low
| Fire closure between Bldg C and AC - Level LB01 and 00 |  | CLOSED | Connection between C and AC are open at level B1 and 00. 10.01: temporary Fire rated partitions and doors have been installed |  | Low
| Cooling system | ACTION | CLOSED |  | 18.11: RPN to confirm cooling system readiness | TOP | 2025-09-07 |  | Matteo Naldi
| Swithes delivery | ACTION | CLOSED | Rack elevation have been approved 03.09: T&C meeting was run 16.09: RPN issue configuration request 22.10: RPN sent request for switch delivery L01 & L03 Bldg. S 05.11: Final inspection to take place 06.11 17.11: Switches have been delivered 07.01: Permision to install the switches have been validated 21.01: ICTS is completing is work | 07.01: Network activation to be achieved +/- 22.01 | High | 2025-09-07 |  | Matteo Naldi | Martina Maffioletti
| FR DOOR to Bldg AC - NCF |  | CLOSED |  | 30.09: RPN to provide update on strategy regarding those doors | Medium
| VAR 576 - BLDG.C - FLS EL AND MH UPDATE | ACTION | CLOSED | 23.12: Step 3 Rev.2 has been submitted |  | Low |  |  |  | Jessica Donatelli
| RFID 1456 - CCO | INFO | CLOSED | 14.01: RPN received new quotation 21.01: RFI has been resubmitted 28.01: RFId has been approved |  | Low
| BTR | ACTION | CLOSED | 30.09: 2 Rack located in Bldg.S are not connected to Bldg C. 22.10: SHP confirmed that all TR must be connected to BTR C as per TD LAN Design | 17.12: Final inspection postponed to 06.01. | High | 2025-01-06 |  | Matteo Naldi
| CAR - Cooling T&C + OIBT Certificate | ACTION | CLOSED | 07.11: [Post 12WLA note] CAR PFT requires Cooling to be functioning 07.11: CAR will be ready for testing around 15.12 12.11: Cooling loop to be started in January 16.12: Final inspection was positive 16.12: Cooling system has been completed & ready to be started 07.01: VERTIC system inspected, T&C will be run after VISUALS complete instalation. 14.01: cooling loop to be turned on +/- 17.01 |  | High | 2026-01-19 |  | Matteo Naldi | Leonardo Valentinotti
| COUNCIL CHAMBER - INS 525 Speaker location | ACTION | CLOSED | 08.12: INS 525 has been submitted 19.01: RFID 1473 21.01: Test have been run | 04.02: SHP to approve the report | High
| PRESS BAR - VAR 647 Bldg C IT connection & Electrical sockets | ACTION | CLOSED | 08.12: actula design include 220V for coffee machine and cold room instead of 380V 10.12: SOMBP submited draft 29.02: Step 3 has been issued. 18.02: IT design is not part of CDP 04.03: Civil part has been implemented | 02.02: RPN to proceed 16.02: RPN to issue commercial proposal | High
| PRESS BAR - Stone installation |  | CLOSED | 11.02: All stones have been delivered. 26.02: Floor completed, column clading on going |  | Medium | 2025-12-05 |  | Matteo Naldi | Dario Cavalcoli
| PRESS BAR - Stone mockup | ACTION | CLOSED | 03.09: Stone to be delivered 1st batch 15.09 - 2nd batch 15.10 Bar to be install 15.11. 24.09: RPN is erecting the bench without apporved mockup 01.10: VIGANO to supply mock up by +/- 08/10. 15.10: Stone to be delivereed 16.10 29.10: preparatory works started. 03.11: cushion mock-up has been approved 18.02: Floor stone to be completed this week | 18.02: Bench mockup to be presented this week | High | 2026-01-21 |  | Matteo Naldi | Chiara Re Depaolini
| RFID 1477 |  | CLOSED | 29.01: Approved |  | High
| COUNCIL CHAMBER - INS 535 Coordination on AV equipment |  | CLOSED | 24.11: Perforation have not been executed as per approved dwg. due to non coordinated AV/ arch dwg. 01.12: INS 535 has been issued. 09.01: Step 2 has been issued, RFID 1486 |  | Medium
| COUNCIL CHAMBER - VAR 628 - AV VARIATION | INFO | CLOSED | 25.06 - Led wall adjustment (structure & boxing). 26.11: TELEVIC to be on a separated VAR. 21.01: all electrical modifications linked to F15 panel to be included in this VAR 04.02: VAR is on signature. 11.02: VAR step 4 has been issued. |  | TOP | 2026-02-13 |  | Federica Brunone
| TR 4 VAR 575 - AV TR move for Room 1 |  | CLOSED | 03.12: No technical issue - but commercial 16.01: Commercial agreement 21.01: VAR 575 received by EGGTELSA, procurement on going 04.02: Step 4 has been issued |  | Medium
| SALLE C6 - Carpet | ACTION | CLOSED | 11.02: Carpet installation to start 13.02 | 18.02: Mockup of AV equipment + furniture will be displayed next week. | Medium |  |  | Matteo Naldi
| FIRE DAMPERS - INS 546 |  | CLOSED | 28.01: Fire dampers to be installed per TD | 28.01: RPN to proceed | Medium
GENERAL | IT System Integrator |  | CLOSED | 17.11: Guillermo announced its departure by end December | 17.11: RPN to urge replacement | Low | [10 empty] | #VALUE! | #VALUE! | 185 | #VALUE! | #VALUE! | C1 | #VALUE!
L03 | NCF 355 - Trench produced without approval of INGENI (Office next to Salle IV) |  | CLOSED | 03.11: Site visite have been organised. Trench vave been infiled with approved product 11.11: New trench have been open without the approval of INGENI | 03.11: RPN to properly level the floor and submit photos of executed works | Medium
L02 | SAS to COUNCIL CHAMBER - VAR 473 Ceiling finishes / Fire curtains |  | CLOSED |  | See bellow L01 COUNCIL CHAMBER | High | [10 empty] | #VALUE! | #VALUE! | 187 | #VALUE! | #VALUE! | C1 | #VALUE!
L01 | SALON TCHEQUE - RFId 1446 | ACTION | CLOSED |  | 26.11: RPN/G&T to achieve commercial agreement | High | [10 empty] | #VALUE! | #VALUE! | 188 | #VALUE! | #VALUE! | C1 | #VALUE!
L01 | SALON TCHEQUE - Recabling of balcony |  | CLOSED |  | 26.11: RPN to assess scope of work | Medium | [10 empty] | #VALUE! | #VALUE! | 189 | #VALUE! | #VALUE! | C1 | #VALUE!
L01 | COUNCIL CHAMBER - Curtains motor compatibility with KNX |  | CLOSED | 22.10: RPN have conducted preliminary test. 26.11: EGGTELSA confirmed that motors are compatible |  | Low | [10 empty] | #VALUE! | #VALUE! | 190 | #VALUE! | #VALUE! | C1 | #VALUE!
L00 | UNTV - Radiators |  | CLOSED | 25.11: Issue has been detected on radiator of control room. radiator has been dismounted. VISUALS is blocked for installing AV equipments. | 26.11: RPN to confirm planning of remedials works. | Low | [10 empty] | #VALUE! | #VALUE! | 191 | #VALUE! | #VALUE! | C1 | #VALUE!
L00 | UNTV - Blinds & Automatic windows INS 538 |  | CLOSED | 21.11: Motorized windows were opened damaging the blinds VISUALS will be delayed waitinf for blinds replacement 26.11: Replacement will be received 25.11: UNTV ventilation is ensured by double flow ventilation. Motorized windows are not necessary 03.12: order has been confirmed 08.12: SOMBP issued INS 538. 09.12: VISUALS is stoped on 2 desks 17.12: Blinds have been replaced |  | High | [10 empty] | #VALUE! | #VALUE! | 192 | #VALUE! | #VALUE! | C1 | #VALUE!
L00 | UNTV - NCF 346 drilling of concrete slab |  | CLOSED | 25.07: NCF 346 will be issued concerning the drilling of the concrete slab in C.1-3 & C.1-4 |  | High | [10 empty] | #VALUE! | #VALUE! | 193 | #VALUE! | #VALUE! | C1 | #VALUE!
L00 | UNTV - VAR 612 (revision of VAR 173 - AV UNTV) |  | CLOSED | 14.05: VAR 173 to be re-open 14.05: RPN to raise RFI regarding BROADCAST CDP RPN Design to be checked by sombp in case additional equipments are needed 23.12: Step 4 has been issued |  | High | [10 empty] | #VALUE! | #VALUE! | 194 | #VALUE! | #VALUE! | C1 | #VALUE!
L00 | PRESS BAR - STO ceiling Fire closure |  | CLOSED | 01.10: NCF 367 + related TCI |  | Medium | [10 empty] | #VALUE! | #VALUE! | 195 | #VALUE! | #VALUE! | C1 | #VALUE!
L00 | PRESS BAR - STO ceiling Finishes |  | CLOSED | 29.10: STO in bar area will be completed after bar equipment instalation 03.12: SHP issue comments |  | Medium | [10 empty] | #VALUE! | #VALUE! | 196 | #VALUE! | #VALUE! | C1 | #VALUE!
L00 | PRESS BAR - INS 273 Radiator |  | CLOSED | INS issued 2023 RPN request a VAR |  | Low | [10 empty] | #VALUE! | #VALUE! | 197 | #VALUE! | #VALUE! | C1 | #VALUE!
L00 | PRESS BAR - Resume of operation |  | CLOSED | 07.11: Press Bar to be operational next year 01.12: Cold room RPN mistake? Coffee machine SOMBP mistake? 03.12: VAR 647 has been issued |  | Low | [10 empty] | #VALUE! | #VALUE! | 198 | #VALUE! | #VALUE! | C1 | #VALUE!
LB01 | SALLE C6 - Specific lighting fixtures |  | CLOSED | 07.01: All lighting have been approved |  | Low | [10 empty] | #VALUE! | #VALUE! | 199 | #VALUE! | #VALUE! | C1 | #VALUE!
| AREAS NOT COVERED BY TD - to be painted |  | CLOSED |  | 27.08: RPN to submit markup dwg to clarify areas not covered by TD to be painted. | Medium | [10 empty] | #VALUE! | #VALUE! | 200 | #VALUE! | #VALUE! | C1 | #VALUE!
RFI 1391 | Meeting room AV VAR 299 |  | CLOSED | 02.04: [Ben lang] Room C427 is not accessible for disable 16.04: that RPN has all the information needed to proceed with the design of the AV - no need to issue a new INS since INS-352 contains the layout that RPN thought they were missing. 27.08: RFI 1391 have been rejected | 25.06: SOMBP / SHP to comment RFI 1391 | Medium | [10 empty] | #VALUE! | #VALUE! | 201 | #VALUE! | #VALUE! | C1 | #VALUE!
T&C - Section of works | Section of works Testing & commissioning plan |  | CLOSED | 16.10: to be submitted 6 months before Substantial completion | 16.10: RPN to submit updated Section Of Works T&C plan | High | [10 empty] | #VALUE! | #VALUE! | 202 | #VALUE! | #VALUE! | C1 | #VALUE!
T&C - IT Network Activation | Pre-requisite |  | CLOSED | 19.11: activation +/- 2-3 weeks 15.12 UPS panel Final inspection |  | High | [10 empty] | #VALUE! | #VALUE! | 203 | #VALUE! | #VALUE! | C1 | #VALUE!
R-VAR-0473 | #N/A |  | CLOSED | #N/A | 14.01: sliding door dwg to be submitted this week. (@ entrance C6) 28.01: Dorma kabba taking measurements to issue dwg 03.02: RPN to submit Coordinated dwg. VAR to bedetermined. 04.02: step 4 (determination) on signature. 18.02 step 4 signed 18.02: RPN to issue dwg 25.02: RPN / SOMBP to coordinate dwg | #N/A | [10 empty] | ---160C1N----160C1N | ---160C1N----160C1N | 204 |  |  | #REF! | Y
R-VAR-0515 | #N/A | INFO | CLOSED | #N/A | 14.01: Dwg submitted by RPN. Pxt MH dwg + ATI dwg to be submitted this week. 21.01: SOMBP / SHP to comment 28.01: SOMBP / SHP to comment 25.02: [Bldg A] SHP to revise including Concordia. | #N/A | [10 empty] | ---160C1N----160C1N | ---160C1N----160C1N | 205 |  |  | #REF! | Y
R-VAR-0526 | #N/A | INFO | CLOSED | #N/A | 04.06: VAR is put on hold. | #N/A | [10 empty] | ---160C1N----160C1N | ---160C1N----160C1N | 206 |  |  | #REF! | Y
VAR 456 | COUNCIL CHAMBER EMERGENCY Light | ACTION | CLOSED | 08.10: Cables will not be changed |  | TOP
VAR 417 | COUNCIL CHAMBER HEATING COILS BMS | ACTION | CLOSED |  | 03.10: RPN to confirm status on site | TOP
VAR 294 | LOCKING SYSTEM FOR EXISTING DOORS ON ESCAPE ROUTES | ACTION | CLOSED |  | 03.10: RPN to confirm implementation in door schedule | Medium
VAR 175 | PARKING P3 drainage | ACTION | CLOSED |  | 03.10: RPN to confirm feasability before S/C | Medium
GENERAL | QUALITY Pre-reception procedure |  | CLOSED | 30.04: No clear procedure | 30.04: RPN/ SHP to clarify on site pre-reception procedure. 21.05: SBIS to confirm | Medium | [10 empty] | #VALUE! | #VALUE! | 211 | #VALUE! | #VALUE! | C1 | #VALUE!
L05 | HANDRAIL in STAIRCASE 5 |  | CLOSED | 30.09: Handrail already produced | 30.09: RPN to update dwg | Medium | [10 empty] | #VALUE! | #VALUE! | 212 | #VALUE! | #VALUE! | C1 | #VALUE!
L04 | SECURITY Dwg |  | CLOSED |  | 30.09: RPN to organize a session to clear topics on rejected dwg 23.10: RPN to share excell files, SOMBP/ SHP to assess | Medium | [10 empty] | #VALUE! | #VALUE! | 213 | #VALUE! | #VALUE! | C1 | #VALUE!
L03 | SALLE IV - INS 5 Perforation from Salle IV to Salon Français (emergency light) |  | CLOSED | 30.09: Cut in carpet have been done SHP require to move rack from Salle IV to xxx 12.11: Conduit have been installed RPN to inform SOMBP/ SHP of any structural modification | 30.09: RPN to present works 22.10: RPN to install conduit 22.10: SHP to issue INS (RPN will issue RFI daywork) | High | [10 empty] | #VALUE! | #VALUE! | 214 | #VALUE! | #VALUE! | C1 | #VALUE!
L03 | ROOF |  | CLOSED | 30.09: Works have been inspected 2 years ago. | 30.09: Works to be tested | Low | [10 empty] | #VALUE! | #VALUE! | 215 | #VALUE! | #VALUE! | C1 | #VALUE!
L01 | SALON FRANCAIS - Wifi | INFO | CLOSED | 05.11: 1 Wifi can not been installed as designed 12.11: 1 WIFI is suficiant per predictive survey 19.11: RPN to proceed with 1 WIFI. efficiency to be check at S.C. | 12.11: RPN to initiate physical survey. KYOS to intervene on site. 19.11: RPN to proceed with 1 WIFI | High | [10 empty] | #VALUE! | #VALUE! | 216 | #VALUE! | #VALUE! | C1 | #VALUE!
GENERAL | EGGTELSA |  | CLOSED | 07.01: EGGTELSA is working on site, but not attending any meeting 14.01: EGGTELSA / RPN Commercial discussion are ongoing |  | Low | [10 empty] | #VALUE! | #VALUE! | 217 | #VALUE! | #VALUE! | C1 | #VALUE!
L03 | SALLE IV (Salon Roumain) - Connection between Salle IV & C210 | INFO | CLOSED | 02.10: SHP shared dwg 02.10: RPN to install duct. Cat.7 cable will be pulled by FMS. 15.10: RPN Have requested offer to EGGTELSA 05.11: Works ongoing |  | Low | [10 empty] | #VALUE! | #VALUE! | 218 | #VALUE! | #VALUE! | C1 | #VALUE!
L01 | COUNCIL CHAMBER - AV DESIGN |  | CLOSED | 15.01: Dwg uploaded on pmweb | 17.12: RPN to asses potential dwg to be resubmted/ checked/ assessed | High | [10 empty] | #VALUE! | #VALUE! | 219 | #VALUE! | #VALUE! | C1 | #VALUE!
L01 | FIXED FURNITURES DESCOPE - VAR 64 / INS 528 |  | CLOSED | 29.10: dwg have been approved including furnitures that were descope with VAR 64. 30.10: SHP email RPN 27.11: INS 528 has been submitted 10.12: VAR needed, cable to be replaced, cable to run at level B01 | 03.12: SHP to update Sketch (bulkhead is clashing with ventilation duct) | Medium | [16 empty] | #VALUE!
LB01 | SALLE C6 - Furniture delivery | INFO | CLOSED | 27.10: delivery by the 3rd week of january. 29.10: completion of salle C5 by end of march. 22.12: Furnitures will be delivered by 14.01. 14.01: Furnitures have been delivered. |  | Low | [10 empty] | #VALUE! | #VALUE! | 222 | #VALUE! | #VALUE! | C1 | #VALUE!
LB01 | SALLE C6 - Raised floor NCF 374 | ACTION | CLOSED | 12.12: QI 544 have been updated. 21.01: NCF has been closed |  | Low | [10 empty] | #VALUE! | #VALUE! | 223 | #VALUE! | #VALUE! | C1 | #VALUE!
LB02 | Existing cables transiting through vertical escape route |  | CLOSED | 03.12: Vertical escape route (Stair 6) = cables to be covered (EI30) 17.12: SOMBP issued INS (cables to be encased over 20m) | 17.12: RPN to assess potential cable replacement | High | [10 empty] | #VALUE! | #VALUE! | 224 | #VALUE! | #VALUE! | C1 | #VALUE!
LB02 | INS 496 Radiator |  | CLOSED | 03.12: RPN requires VAR |  | High | [10 empty] | #VALUE! | #VALUE! | 225 | #VALUE! | #VALUE! | C1 | #VALUE!
MAS 442 & 443 | Acoustical foam |  | CLOSED | 11.06: SOMBP alerted Kopitsis 18.06: SOMBP refused the MAS (Highly inflamable + low acoustical performance) | 09.07: RPN to comment 06.08: RPN will send an email. | Low | 2025-06-10 |  | Davide Cirillo | [7 empty] | #VALUE! | #VALUE! | 226 | #VALUE! | #VALUE! | C1 | #VALUE!
Note on F201: Add Pierre

## OWNER LIST
Owner Name | Email | Owner ORG | Role | Main ORG | No sharepoint | NameforMondayemail | ACRONYM
Abigail Abraham | donatella.rocca@un.org | MSTEP | TBC | SOMBP | abigail@mstep.co.uk | Abigail
Alan McBryan | alan.mcbryan@aecom.com | AECOM | MEP Manager | SOMBP |  | Alan
Alastair Wolstenholme | a.wolstenholme@gardiner.com | G&T | Senior Associate - Cost Management and Contract Administration | G&T |  | Alastair
Alberto Mastrangelo | pme_to.srl@libero.it | PME | TBC | RPN |  | Alberto
Alex Graham | alexander.graham1@un.org | SHP | Cost Management | SHP |  | Alex
Alexandre ROUVELET | alexandre.rouvelet@projection-nouvelle.com |  | Overall System Engineer |  |  | Alexandre
Alessandro Manfredi
Alistair Wade | a.wade@gardiner.com | G&T | Cost Management | G&T |  | Alistair
Amos Anderini | amos.anderini@rpn-sa.ch | RPN | Deputy HSE & Security Manager | RPN |  | Amos
Andrea Falchi | andrea.falchi@c2be.uno | C2BE | TBC | C2BE |  | Andrea
Andrea Hoffman | ahoffmann@hoffmannart.ch | SHP | Heritage/Art Expert | SHP |  | Andrea
Andrea Sigona | bob.wyse@som.com | SOMBP | Senior Architect | SOMBP |  | Bob
Andrea VANOSSI | a.vanossi@gmail.com |  | BIM Manager |  |  | Andrea
Andrei Misaila | septimiu.misaila@un.org | UN | TBC | UN |  | Andrei
Barry Poling | barry.poling@aspenglobal.co.uk | ASPEN | Lean Consultant | ASPEN |  | Barry
Ben Lang | blang@smwllc.com | SMW | TBC | SOMBP |  | Ben
Benoit Renault | benoit.renault@un.org | SHP | Senior Electrical Engineer | SHP |  | Benoit
Bernard Mégevand | bernard.megevand@sbis.ch | SBIS | TBC | SOMBP |  | Bernard
Bhav | bhav@mstep.co.uk | MSTEP | TBC | SOMBP |  | Bhav
Billy Clayton | b.clayton@Gardiner.com | G&T | Cost Management | G&T |  | Billy
Blaise BOURGEOIS | bb@oxalis-landscape.ch |  | Associate Director |  |  | Blaise
Bob Wyse | bob.wyse@som.com | SOMBP | Architect | SOMBP |  | Bob
Calum Redfern | c.redfern@gardiner.com | G&T | Cost Management | G&T |  | Calum
Catherine Isabella | catherine.isabella@burckhardt.swiss | SOMBP | Architect | SOMBP |  | Catherine
Cedric Erard | ce@erard.biz | SOMBP | MEP Manager | SOMBP |  | Cedric
Cedric Kusendova | cedric.kusendova@un.org | SHP | MEP Manager | SHP |  | Cedric
Charles de Crisenoy | didier.dequatre@un.org | SHP | Quality Manager | SHP |  | Didier
Chiara Re Depaolini | chiara.redepaolini@rpn-sa.ch | RPN | Arch Design Specialist | RPN |  | Chiara
Chris Welch | c.welch@gardiner.com | G&T | Cost Management | G&T |  | Chris
Christian Bona | christian.bona@rpn-sa.ch | RPN | MEP Manager | RPN |  | Christian
Cinzia Porracin | porracin@un.org | SHP | Security Site Construction Management | SHP |  | Cinzia
Clare O'Malley | c.omalley@gardiner.com | G&T | Cost Management | G&T |  | Clare
Consuelo Crespi | consuelo.crespi@csc-sa.ch | C2BE | H&S Manager | C2BE |  | Consuelo
Cormac Mc Gavigan | cormac.mcgavigan@csc-sa.ch | C2BE | Electrical Design Lead | C2BE |  | Cormac
Craig McLellan | c.mclellan@gardiner.com | G&T | Partner - Cost Management | G&T |  | Craig
Damien Fesselet | damien@ecoservices.ch | Ecoservices | TBC | SOMBP |  | Damien
Damien Papuchon | damien.papuchon@un.org | UN | TBC | UN |  | Damien
Danielle Boyd | danielle.boyd@burckhardt.swiss | SOMBP | TBC | SOMBP |  | Danielle
Dario Cavalcoli | dario.cavalcoli@un.org | SHP | Senior Architect - Lead PCS | SHP |  | Paolo
David Goetz | dgoetz@smwllc.com | SOMBP | TBC | SOMBP |  | David
David Heison | david.heison@un.org | SHP | Handover and Commissioning Management | SHP |  | David
David R. HARVEY | david@hmb-a.com |  | Associate |  |  | David
Davide Cirillo | davide.cirillo@cmbcarpi.it | RPN | Quality Manager | RPN |  | Davide
Deán de Klerk | dean.deklerk@un.org | SHP | Project Schedule Manager | SHP |  | Deán
Didier Chessel | didier.chessel@un.org | SHP | Health and Security Coordinator | SHP |  | Didier
Didier Dequatre | didier.dequatre@un.org | SHP | Quality Manager | SHP |  | Didier
Dima Khoury | dima.khoury@un.org | UN | TBC | UN |  | Dima
Dominic Walther | dominic.walther@burckhardt.swiss | SOMBP | Design and Construction Director | SOMBP |  | Dominic
Dominique Hirigoyen | dominique.hirigoyen@un.org | UN | electronic engineering technician | UN |  | Dominique
Donatella Rocca | donatella.rocca@un.org | SHP | Documents Manager | SHP |  | Donatella
DOR_D | donatella.rocca@un.org | SHP | TBC | SHP |  | Donatella
DOR_N | donatella.rocca@un.org | SHP | TBC | SHP |  | Donatella
DOR_M | donatella.rocca@un.org | SHP | TBC | SHP |  | Donatella
DOR_P | donatella.rocca@un.org | SHP | TBC | SHP |  | Donatella
DOR_D | natalie.hilen@un.org | SHP | TBC | SHP |  | Natalie
DOR_N | natalie.hilen@un.org | SHP | TBC | SHP |  | Natalie
DOR_M | natalie.hilen@un.org | SHP | TBC | SHP |  | Natalie
DOR_P | natalie.hilen@un.org | SHP | TBC | SHP |  | Natalie
Dounia Zine | dounia.zine@csc-sa.ch | C2BE | Document Manager | C2BE |  | Dounia
Dragos Ionescu | ionescud@un.org | SHP | ICTS Operational Expert | SHP |  | Dragos
Elaine Hunter | e.hunter@gardiner.com | G&T | Cost Management | G&T |  | Elaine
Elliot Cordery | e.cordery@gardiner.com | G&T | Cost Management | G&T |  | Elliot
Elsa Briot | elsa.briot@som.com | SOMBP | Project Manager | SOMBP |  | Elsa
Emerson Njouokou | emerson.njouokou@nembrini.com | NEMV | TBC | RPN |  | Emerson
Emilio Mariani | emilio.mariani@csc-sa.ch | C2BE | Business Continuity Manager | C2BE |  | Emilio
Eric Dubouloz | eric@ecoservices.ch | Ecoservices | TBC | SOMBP |  | Eric
Eric JAZARGUER | e.jazarguer@eggtelsa.com | Eggtelsa | KNX expert | RPN |  | Eric
Eric Oller | eric.oller@un.org | SHP | Project Manager | SHP |  | Eric
Ethan Liu | ethan.liu@som.com | SOMBP | TBC | SOMBP |  | Ethan
Fabio Marcelli | fabio.marcelli@csc-sa.ch | C2BE | TBC | RPN |  | Fabio
Federica Brunone | federica.brunone@cmbcarpi.it | RPN | Engineering Chief & Move Manager | RPN |  | Federica
Federica Chiericato | federica.chiericato@csc-sa.ch | C2BE | Design programme change manager | C2BE |  | Federica
Fiona Esler | fiona@mstep.co.uk | MSTEP | TBC | SOMBP |  | Fiona
Florian Cochard | f.cochard@eggtelsa.com | Eggtelsa | Electrical Engineer | RPN |  | Florian
Francesco Pieri | francesco.pieri@rpn-sa.ch | RPN | HSE Assistant | RPN |  | Francesco
Francesco Sambucini | francesco.sambucini@rpn-sa.ch | RPN | HSE Deputy Manager | RPN |  | Francesco
Franck Reynaud |  | Visuals | TBC | RPN | franck@visuals.ch | Frank
Frank Lambelet | lambelet@bcs-facades.ch | Bcs facades | TBC | SOMBP |  | Frank
Frederic Solda | frederic.solda@csc-sa.ch | C2BE | Planner Manager | C2BE |  | Frederic
Gabriele Provenzale | gabriele.provenzale@csc-sa.ch | C2BE | Design/Construction Manager CSA | C2BE |  | Gabriele
Gary Thornton | gary@nultylighting.co.uk | Lighting | Lighting | SOMBP |  | Gary
Geoffrey Pillitteri | geoffrey.pillitteri@un.org | UN | TBC | UN |  | Geoffrey
Gerald Robinson | gerald@aspenglobal.co.uk | ASPEN | Lean Consultant | ASPEN |  | Gerald
Giada Savini | giada.savini@rpn-sa.ch | RPN | Senior Architect | RPN |  | Giada
Gianluca Crippa | gianluca.crippa@rpn-sa.ch | RPN | Construction Manager | RPN |  | Gianluca
Giulia Amendola | giulia.amendola@rpn-sa.ch | RPN | TBC | RPN |  | Giulia
Giulia Putaturo | g.putaturo@fratellinavarra.it | RPN | Heritage/Art Expert | RPN |  | Giulia
Goran Josipovic | goran.josipovic@wsp.com | Lift | TBC | SOMBP |  | Goran
Gregory Baubiet | lucille.treilledegrandsaigne@burckhardt.swiss | SOMBP | Architect | SOMBP |  | Gregory
Guillermo Garcia | guillermo.garcia@afry.com | AFRY |  | SOMBP |  | Guillermo
Hacir Degirmencioglu | hacir.degirmencioglu@rpn-sa.ch | RPN | Electrical Engineer | RPN |  | Hacir
Hamza Haouass | hamza.haouass@csc-sa.ch | C2BE | TBC | RPN |  | Hamza
Helen Shreeve | h.shreeve@gardiner.com | G&T | Cost Management | G&T |  | Helen
Ibtisam Naym | ibtisam.naym@rpn-sa.ch | RPN | Documents Manager | RPN |  | Ibtisam
Ishac Koussa | ishac.koussa@som.com | SOMBP | TBC | SOMBP |  | Ishac
Jaime Gutierrez | jaime.gutierrez@burckhardt.swiss | SOMBP | Architect | SOMBP |  | Jaime
James Staunton | james.staunton@aecom.com | AECOM | TBC | SOMBP |  | James
Jean-Marc Glinz | jean-marc.glinz@un.org | UNTV | Chief of unit, Public information | UN |  | Jean-Marc
Jean-Mathieu Ferre | jean.ferre@un.org | SHP | Design Manager (DM) | SHP |  | Jean-Mathieu
Jeremy Theniere | jeremy.theniere1@un.org | SHP | Move expert | SHP |  | Jeremy
Jérôme Colder | j.colder@jdrenergies.ch | AECOM | TBC | SOMBP |  | Jérôme
Jérome MATRINGE | jerome.matringe@projection-nouvelle.com |  | Technical on-site Manager |  |  | Jérome
Jérôme POCHAT | jerome.pochat@ingeni.ch |  | Partner |  |  | Jérôme
Jessica Donatelli | jessica.donatelli@cmbcarpi.it | RPN | Cost Control Manager | RPN |  | Jessica
Joachim de Roquefeuil | joachim.deroquefeuil@sbis.ch | SBIS | TBC | SOMBP |  | Joachim
Joe Gul | j.gul@gardiner.com | G&T | Assistant Cost Management and Contract Administration | G&T |  | Joe
Joel Benghiat | joel.benghiat@nembrini.com | NEMB | TBC | RPN |  | Joel
John Rutter | john@aspenglobal.co.uk | ASPEN | Lean Consultant | ASPEN |  | John
Joseph Christi | jchristi@smwllc.com | SMW | TBC | SOMBP |  | Joseph
Josiah Abraham | josiah@mstep.co.uk | MSTEP | Mechanical Engineer | SOMBP |  | Josiah
Julia Skeete | julia.skeete@som.com | SOMBP | Project Director (PD) | SOMBP |  | Julia
Kateryna Starykova | kateryna.starykova@un.org | SHP | Senior Electrical Engineer | SHP |  | Kateryna
Katherine Pink | katherine.pink@som.com | SOMBP | Design and Construction Director | SOMBP |  | Katherine
Kayci BROWNE | kbrowne@un.org |  | Transition Program. Manag. Officer |  |  | Kayci
Kenneth Potgieter | k.potgieter@gardiner.com | G&T | Cost Management | G&T |  | Kenneth
Laetitia Menin | laetitia.menin@un.org |  | Engineer, Buildings Unit, Facility Management Section |  |  | Laetitia
Laurent Sailler | laurent.sailler@rapp.ch | RAPP | TBC |  |  | Laurent
Leonardo Castellani | leonardo.castellani@trepi.it | 3PI | AV and Broadcast Expert | RPN |  | Leonardo
Leonardo Deliaj | sldeliaj@dallmanagement.com | RPN | MEP Manager | RPN |  | Leonardo
Leonardo Valentinotti | leonardo.valentinotti@rpn-sa.ch | RPN | Deputy Quality Manager | RPN |  | Leonardo
Liliana Sanches Le Saux | liliana.lesaux@gmail.com | SOMBP | Architect / Accessibility | SOMBP |  | Liliana
Lionel Perrin | lionel.perrin@csc-sa.ch | C2BE | Project Control Manager | C2BE |  | Lionel
Loice Mhuru | l.mhuru@gardiner.com | G&T | Cost Management | G&T |  | Loice
Lorenzo Barnini | lorenzo.barnini@cmbcarpi.it | RPN | Project Manager (PM) | RPN |  | Lorenzo
Lorenzo Fiorucci | lorenzo.fiorucci@csc-sa.ch | C2BE | Project Manager (PM) | RPN |  | Lorenzo
Lorenzo Lelli | lorenzo.lelli@ingeni.ch | Structural | TBC | SOMBP |  | Lorenzo
Lorik Rashica | lrashica@smwllc.com | SOMBP | TBC | SOMBP |  | Lorik
Luca CARLINO | [5 empty] | Luca
Luca Lodi | luca.lodi@cmbcarpi.it | C2BE | Engineering Project Manager - Lead | C2BE |  | Luca
Lucille Treille de Grandsaigne | lucille.treilledegrandsaigne@burckhardt.swiss | SOMBP | Architect | SOMBP |  | Lucille
Luigi Ripamonti | luigi.ripamonti@csc-sa.ch | C2BE | TBC | C2BE |  | Luigi
Luke Coleshill | l.coleshill@gardiner.com | G&T | Cost Management | G&T |  | Luke
Luke Leung | luke.leung@som.com | SOMBP | TBC | SOMBP |  | Luke
Mairi Macintyre | mairi@aspenglobal.co.uk | ASPEN | TBC | ASPEN |  | Mairi
Marc Frezza | marc.frezza@un.org | UNOG | electronic engineering technician | UNOG |  | Marc
Marco Benassi | marco.benassi@un.org | SHP | Archibus | SHP |  | Marco
Marco Miano | marco.miano@trepi.it | 3PI | AV and Broadcast Expert | RPN |  | Marco
MariaCristina Menozzi | mariacristina.menozzi@cmbcarpi.it | RPN | HSE & Security Manager | RPN |  | MariaCristina
Marine Paillance | marine.paillance@burckhardt.swiss | SOMBP | Document Controller | SOMBP |  | Marine
Mark Peacock | mark.peacock@un.org | SHP | Contract Management | SHP |  | Mark | MAP
Martina Maffioletti | martina.maffioletti@rpn-sa.ch | RPN | Move Specialist / Doc Controller | RPN |  | Martina
Martino Zanini | martino.zanini@csc-sa.ch | C2BE | Procurement Engineer | C2BE |  | Martino
Maryna Chernova | maryna.chernova@un.org | SHP | Change Manager | SHP |  | Maryna
Marzio Medaglia | marzio.medaglia@afry.com | RPN |  | RPN |  | Marzio
Massimiliano Binci | massimiliano.binci@ingeni.ch | Ingeni | TBC | SOMBP |  | Massimiliano
Matteo Cremaschi | matteo.cremaschi@trepi.it | 3P | Project Manager (PM) | RPN |  | Matteo
Matteo Naldi | matteo.naldi@cmbcarpi.it | RPN | Construction Manager | RPN |  | Matteo
Matteo Schiatti | matteo.schiatti@maspero.ch |  | Vertical Transportation Project Manager |  |  | Matteo
Mauro Radice | mauro.radice@csc-sa.ch | RPN | Contract Manager | RPN |  | Mauro
Maximilien Montanaro | maximilien.montanaro@un.org | SHP | Senior Architect | SHP |  | Maximilien
Maya FARHAT | maya.farhat@un.org | SHP |  | SHP |  | Maya
Melanie Servante | melanie.servante@som.com | SOMBP | TBC | SOMBP |  | Melanie
Michael Burge | m.burge@gardiner.com | G&T | Cost Management | G&T |  | Michael
Michael Filar | michael.filar@som.com | SOMBP | TBC | SOMBP |  | Michael
Michele Righi | righi@un.org | SHP | Project Manager Lead | SHP |  | Michele
Milton Morais | milton.morais@csc-sa.ch | C2BE | Construction Manager | C2BE |  | Milton
Mirta Mariotti | mirta.mariotti@csc-sa.ch | C2BE | Procurement Controller | C2BE |  | Mirta
Morgane Giorgi | giorgi@kopitsis.com | Kopitsis | TBC | SOMBP |  | Morgane
Natalie Hilen | natalie.hilen@un.org | SHP | Document Manager Assistant | SHP |  | Natalie
Neil Bradley | neil.bradley@un.org | SHP | Chief Design and Construction | SHP |  | Neil
Nicolò Mariotti | nicolo.mariotti@rpn-sa.ch | RPN | TBC | RPN |  | Nicolò
Nigel Burch | n.burch@gardiner.com | G&T | Cost Management | G&T |  | Nigel
Noireeta Chowdhury | noireeta.chowdhury@un.org | SHP | Business Continuity Manager | SHP |  | Noireeta
Olivier BLAIN | olivier@media-vision.com |  | Reponsible for Taiden Equipment |  |  | Olivier
Olivier Zuercher | olivier.zuercher@sbis.ch | SBIS | TBC | SOMBP |  | Olivier
Oriol Rovira | o.rovira@energymgt.ch | Energy Mgt | TBC | RPN |  | Oriol
Osamu Moser | om@oxalis-landscape.ch | Oxalis | TBC | SOMBP |  | Osamu
Paolo Bozzetti | paolo.bozzetti@trepi.it | 3PI | AV and Broadcast Expert | RPN |  | Paolo
Patrick Fowler | patrick.fowler@un.org | SHP | Project Manager (PM) | SHP |  | Patrick
Patrick Vogelsang | patrick.vogelsang@un.org | SHP | AV and Broadcast Expert | SHP |  | Patrick
Pietro Redaelli | BIM Coordinator | RPN |  | RPN |  | Pietro
Pav | pav@mstep.co.uk | MSTEP | TBC | SOMBP |  | Pav
Quentin DERAIL | quentin@ecoservices.ch | Ecoservices |  | RPN |  | Quentin
Rafael Lyra | donatella.rocca@un.org | C2BE | Mechanical Engineer | C2BE |  | Rafael
Ralph Giebeler | lorenzo.fiorucci@csc-sa.ch | C2BE | Project Manager (PM) | RPN |  | Lorenzo
RAPP |  | RPN | TBC | RPN |  | RAPP
Remi VANDERPLAETSEN | rvanderplaetsen@unog.ch |  | SSS Officer |  |  | Remi
Richard Norbury | richard@mstep.co.uk | MSTEP | TBC | SOMBP |  | Richard
Richard O'Connor | richard@aspenglobal.co.uk | ASPEN | Lean Consultant | ASPEN |  | Richard
Riddhi Bhootda | riddhi@nultylighting.co.uk | Lighting | TBC | SOMBP |  | Riddhi
Rino Carbone | rino.carbone.ext@trepi.it | 3PI | AV Project manager | RPN |  | Rino
Roberto Barone | roberto.barone@csc-sa.ch | C2BE | Quality Manager | C2BE |  | Roberto
Roger Fernandes | roger.fernandes@som.com | SOMBP | Documents Manager | SOMBP |  | Roger
Rosario Marino | rosario.marino@som.com | SOMBP | Architect | SOMBP |  | Rosario
Ross Turnbull | rturnbull@smwllc.com | SMW | TBC | SOMBP |  | Ross
RPN | federica.brunone@cmbcarpi.it | RPN | TBC | RPN |  | RPN
Saber Zitouni | saber.zitouni@un.org | SHP | Senior Mechanical Engineer | SHP |  | Saber
Sabrina Levati | sabrina.levati@csc-sa.ch | C2BE | BIM Manager | C2BE |  | Sabrina
Samantha Karimanzira
Samuel Havis | s.havis@gardiner.com | G&T | Cost Management | G&T |  | Samuel
Samuel Wilson | samuel.wilson@un.org | SHP | Senior Architect | SHP |  | Samuel
Sasha Krstanovic | sasha@mstep.co.uk | MSTEP | TBC | SOMBP |  | Sasha
Septimiu Andrei Misaila | septimiu.misaila@un.org | UN | TBC | UN |  | Andrei
Shailesh Nepal | nepals@un.org | SHP | Contract Management | SHP |  | Shailesh
Silvia Miralles | silvia.miralles@un.org | SHP | Architect / Accessibility / BIM Manager | SHP |  | Silvia
Silvia Molinari | silvia.molinari@un.org | UN | Architect | UN |  | Silvia
Silvia Palhao | silvia.palhao@burckhardt.swiss | SOMBP | Architect | SOMBP |  | Silvia
Simon | simon@aspenglobal.co.uk |  |  |  |  | Simon
Simone Conti | simone.conti@cmbcarpi.it | RPN | Schedule Manager | RPN |  | Simone
Simone di Nola | simone.dinola@rpn-sa.ch | RPN | TBC | RPN |  | Simone
Sonia Jourmad | sonia@media-vision.com |  | Project Manager |  |  | Sonia
Stefano Barone | stefano.barone@csc-sa.ch | RPN | TBC | RPN |  | Stefano
Stephane Poirey | cormac.mcgavigan@csc-sa.ch | UNOG | ICTS | UNOG |  | Cormac
Stephen FARRELL | sfarrell@unog.ch |  | Purchase & transportation section |  |  | Stephen
Stephen Slawsky | slawsky@un.org | SHP | CHIEF OF SERVICE, PROGRAMME MANAGEMENT | SHP |  | Stephen
Steven Truss | steven.truss@wsp.com | WSP | TBC | SOMBP |  | Steven
Teeba Almunshi | teeba@mstep.co.uk | MSTEP | TBC | SOMBP |  | Teeba
Thaer Alsafar | t.alsafar@energymgt.ch | RPN | TBC | RPN |  | Thaer
Thibault Rochette | thibault.rochette@nembrini.com | NEMB | TBC |  |  | Thibault
Tim Barker | tim.barker@aecom.com | AECOM | TBC | SOMBP |  | Tim
Viola Sartori | viola.sartori@cmbcarpi.it | RPN | Deputy Project Manager | RPN |  | Viola
Wolfgang Theiner | wolfgang.theiner@burckhardt.swiss | SOMBP | Quality Manager (QM) | SOMBP |  | Wolfgang
Wouter Smith | wouter.smith@un.org | UNOG | TBC | UNOG |  | Wouter
Yasmin Harris-Boadi | yasmin@mstep.co.uk | MSTEP | TBC | SOMBP |  | Yasmin
Youri Dervin | youri@ecoservices.ch | Ecoservices | TBC | SOMBP |  | Youri
Youssef Mahcene | youssef.mahcene@un.org | SHP | Senior Mechanical Engineer | SHP |  | Youssef
Yvan Ristic | yri@dssa.ch | AECOM | TBC | SOMBP |  | Yvan
Zahid Mir | zmir@smwllc.com | SMW | TBC | SOMBP |  | Zahid
Zeynep Onen | zeynep.onen@un.org | SHP | Architectural Manager | SHP |  | Zeynep

## DELEGATE
ESCALATE | Owner Name
AB+C - 12 WLA AV focus | Jean-Mathieu Ferre
Leadership meeting | Patrick Fowler
Operational Readiness Meeting | Zeynep Onen
PM | Patrick Fowler
R - Architectural meeting | Bob Wyse
UNTV - 12 WLA | Jean-Mathieu Ferre
Site visit

## DISCIPLINE
Discipline | description | RFI / NCF DISCIPLINE | DALUX disciplne | MACRO DISCIPLINE
A | Architecture | A - Architecture | ARCH | ARC
A | Architecture |  | ARCHITECTURAL | ARC
A | Architecture |  | HERI | ARC
A | Architecture |  | HERITAGE | ARC
AI | Architectural Interior | AI - Architectural Interior |  | ARC
AL | Lighting | AL - Lighting |  | ARC
BC | Broadcast | BC - Broadcast | AUDIOVISUAL & BROADCAST | TA
BC | Broadcast |  | AVBC | TA
BIM | BIM | BIM - BIM |  | ARC
CON | Construction | CON |  | CON
EL | Electrical | EL - Electrical | ELECTRICAL/SAFETY/SECURITY | MEP
EL | Electrical |  | ELSS | MEP
ENV | Envelope | ENV - Envelope |  | ARC
FA | Facade | FA - Facade |  | ARC
FP | Fire Protection | FP - Fire Protection |  | ARC
FU | Furniture | FU - Furniture |  | ARC
HM | Hazardous Material | HM - Hazardous Material |  | ARC
KC | Kitchen | KC - Kitchen |  | ARC
LS | Landscape | LS - Landscape |  | ARC
MEP | Combined Plans | MEP - Combined Plans |  | MEP
MH | Mechanical HVAC | MH - Mechanical HVAC | MECHANICAL/PLUMBING | MEP
MH | Mechanical HVAC |  | MHPL | MEP
MH | Mechanical HVAC |  | MP | MEP
PE | Permit | PE - Permit |  | PM
PL | Plumbing | PL - Plumbing | MECHANICAL/PLUMBING | MEP
PL | Plumbing |  | MHPL | MEP
PL | Plumbing |  | MP | MEP
PM | Project Management | PM - Project Management |  | PM
QA | Quality Assurance |  | QA | QUALITY
QC |  |  |  | QUALITY
QM |  |  |  | QUALITY
SE | Structural Existing Buildings | SE - Structural Existing Buildings | STRU | ARC
SE | Structural Existing Buildings |  | STRUCTURE | ARC
SN | Structural New Building |  | STRU | ARC
SN | Structural New Building | SN - Structural New Building | STRUCTURE | ARC
STK | Stakeholders Engagement | STK - Stakeholders Engagement |  | PM
TT | IT | TT - IT | IT | TT
TA | Audiovisuals | TA - Audiovisuals | AUDIOVISUAL | TA
TA | Audiovisuals |  | AUDIOVISUAL & BROADCAST | TA
TA | Audiovisuals |  | AVBC | TA
TY | Security | TY - Security | ELECTRICAL/SAFETY/SECURITY | TY
TY | Security |  | ELSS | TY
VT | Vertical Transportation | VT - Vertical Transportation |  | VT
HSE | Health, Security and Environment | HSE - Health, Security and Environment |  | PM
HSE | Health, Security and Environment |  | ELECTRICAL/SAFETY/SECURITY | PM