MEETING MINUTES

Building C — 12 Week Look Ahead (Production Meeting)

25 February 2026 | Week 9 | Section C

# A — Meeting Details

| Meeting Type | PRODUCTION |
| --- | --- |
| Week No. | 9 |
| Section | C |
| Date | 25 February 2026 |
| Time | 10:30 |
| Location | Building C - R005 |
| Purpose | To support and protect the Production Plan To strive for improved Production Plan stability and predictability. |
| Next Meeting | 04 March 2026 |

# B — Attendees

| Name | Organisation | Present | Role |
| --- | --- | --- | --- |
| Lorenzo Barnini | RPN | Yes | Project Manager (PM) |
| Matteo Naldi | RPN | Yes | Construction Manager |
| Jessica Donatelli | RPN | No | Cost Control Manager |
| Federica Brunone | RPN | Yes | Engineering Chief & Move Manager |
| Chiara Re Depaolini | RPN | No | Arch Design Specialist |
| Simone Conti | RPN | Yes | Schedule Manager |
| Martina Maffioletti | RPN | No | Move Specialist / Doc Controller |
| Hacir Degirmencioglu | RPN | Yes | Electrical Engineer |
| Leonardo Valentinotti | RPN | Yes | Deputy Quality Manager |
| MariaCristina Menozzi | RPN | Yes | HSE & Security Manager |
| Zeynep Onen | SHP | Yes | Architectural Manager |
| Neil Bradley | SHP | Yes | Chief Design and Construction |
| Patrick Fowler | SHP | Yes | Project Manager (PM) |
| Cedric Kusendova | SHP | Yes | MEP Manager |
| Maryna Chernova | SHP | Yes | Change Manager |
| Jean-Mathieu Ferre | SHP | Yes | Design Manager (DM) |
| Kateryna Starykova | SHP | Yes | Senior Electrical Engineer |
| Benoit Renault | SHP | No | Senior Electrical Engineer |
| Didier Dequatre | SHP | Yes | Quality Manager |
| Cedric Erard | SOMBP | Yes | MEP Manager |
| Lucille Treille de Grandsaigne | SOMBP | Yes | Architect |
| Rosario Marino | SOMBP | Yes | Architect |

# C — Action Items

## C2 — PRODUCTION

| Topic | Subject | Type | Priority | Due Date | Action Required | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| GENERAL | Substantial Completion | INFO | High | 06.03.2026 | 25.02: Official S.C. 24.04 (no exclusion). 04.03: RPN to confirm which areas can be delivered on 24.04. | Simone Conti |
| GENERAL | PPC | INFO | Low | — | Electrical installation at LB2 to be resolved. | — |
| GENERAL | Police du Feu | INFO | Medium | — | — | — |
| GENERAL | Windows – NCF 382 (A-AB-C) | ACTION | TOP | 27.02.2026 | 25.02: RPN to organise site inspection with Manufacturer (+/- 03.03). | Davide Cirillo / Didier Dequatre |
| DESIGN | Phase 6 Dwg / As-Built Dwg | INFO | Medium | 13.03.2026 | 04.03: SHP to assess. | Donatella Rocca / Jean-Mathieu Ferre |
| GENERAL | TCI – Follow-Up | INFO | Low | — | — | Martina Maffioletti |
| GENERAL | EGGTELSA | ACTION | TOP | 04.02.2026 | 28.01: RPN to present a synthesis of issues and impact on delay. | Matteo Naldi |
| GENERAL | Fire Matrix | INFO | TOP | 05.03.2026 | 23.02: RPN to assess +/- 05.03. | Federica Brunone |
| GENERAL | Fire Hoses | ACTION | High | 30.04.2026 | Fire hoses to be T&C + certified. PXT to submit report. | Martina Maffioletti / Amos Anderini |
| GENERAL | Fire Fighter Route – INS 421 / VAR 536 | ACTION | High | 08.02.2026 | 21.01: RPN to plan execution in AC and S1. | Matteo Naldi |
| GENERAL | VIGANO – Wooden Doors / Windows Frame / Furnitures | INFO | TOP | 05.03.2026 | Priorities: A.13 (high risk), CAR @LB01, Salle C6 interpreter booth, UNTV, Corridors L05-L03, Offices L05-L03, Salon Tcheque, Council Chamber. | Matteo Naldi / Lorenzo Barnini |
| GENERAL | Lifts – Planning | ACTION | High | 02.10.2025 | 07.01: RPN to update planning. | Gianluca Crippa |
| LIFTS | Lift 5, 6, 23 – Platform C6, C5 | ACTION | TOP | 18.02.2026 | 11.02: RPN to check if Platform C5 is working. | Matteo Naldi |
| EMERGENCY LIGHT | VAR 221 | ACTION | TOP | 11.02.2026 | 11.02: RPN to assess – 4 irrelevant elements in balance. SHP to issue Step 4. | Clare O'Malley |
| FIRE CURTAINS | Fire Curtains (8#) – OIBT | ACTION | High | 28.01.2026 | RPN to confirm delivery and planning of fire curtains. | Matteo Naldi / Simone Conti |

## C2 — PRODUCTION (Levels)

| Topic | Subject | Type | Priority | Due Date | Action Required | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| L05-L03 | Displays in Meeting Rooms – VAR 478 | ACTION | High | 06.03.2026 | 25.02: VAR 478 to be updated (TV size 65" = 75"). 04.03: SHP to issue revised Step 4 – G&T to assess. | Clare O'Malley |
| L05 | WiFi | ACTION | High | 10.10.2025 | New simulation to be run. RPN consultant to run physical survey with ICTS and modify WAPs configuration. | Dragos Ionescu / Jean-Mathieu Ferre |
| L04 | Meeting Room L05 – VAR 659 – Obsolete Luminaires | ACTION | High | 26.02.2026 | 04.03: SOMBP/SHP to assess if luminaire can be descoped. 09.03: SOMBP to issue VAR to descope luminaire. | Cedric Erard |
| L01 | Salon Tcheque – Works | INFO | TOP | 10.02.2026 | — | Matteo Naldi |
| L01 | Salon Tcheque – Back Door Entrance @L02 | ACTION | High | 20.03.2026 | — | Matteo Naldi |
| L01 | Salon Tcheque – Relamping | ACTION | High | 25.02.2026 | 23.02: SHP to raise TCI. | Maximilien Montanaro |
| L01 | Salon Francais – Wall Mounted Lighting | ACTION | Medium | 05.11.2025 | 03.11: Condition report to be checked. | Maximilien Montanaro |
| L01 | Salon Francais – Damaged Carpet | ACTION | Low | 05.03.2026 | RPN to propose solution + liaise with heritage specialist. | Maximilien Montanaro |
| L01 | Salle 1 – Relamping | ACTION | High | 16.03.2026 | 09.03: RPN to proceed. | Matteo Naldi |
| L01 | Salle 1 – NCF 380 – Conditions AV Equipment | ACTION | Medium | 25.02.2026 | 23.02: RPN to assess. | Davide Cirillo |
| L02 | SAS to Council Chamber – VAR 570 – LED Integration | ACTION | TOP | 23.02.2026 | 09.02: RPN to issue Step 2. 23.02: RPN to issue commercial proposal. | Jessica Donatelli |
| L01 | Council Chamber – VAR 399 – Balustrade to Coursive | ACTION | TOP | 06.03.2026 | 04.02: RPN to confirm (refer to technical solution applied in Hall 14 mezzanine). | Chiara Re Depaolini |
| L01 | Council Chamber – VAR 539 – Conference Door | ACTION | High | 20.03.2026 | 23.02: SHP to update VAR 539 including Council Chamber doors. | Maximilien Montanaro |
| L01 | Council Chamber – LED Wall Ventilation Issue | ACTION | High | 06.03.2026 | 26.02: RPN to reject delivery / submit manufacturer warranties. | Federica Brunone |
| L01 | Council Chamber – VAR 625 – Electrical Panel F15 | INFO | High | 06.03.2026 | 04.03: Final Inspection planned for week 09.03. | Hacir Degirmencioglu |
| L01 | NCF 357 – AV Cables Quality | ACTION | High | 02.12.2025 | 24.11: RPN to comment. | Davide Cirillo |
| L01 | Stair 6 Lighting | ACTION | Medium | 29.01.2026 | 04.03: RPN to issue updated MAS. | Hacir Degirmencioglu |
| L00 | UNTV – Flash Light + PA Speaker / RFID 1489 – INS 544 | ACTION | TOP | 04.02.2026 | 4.02: RPN to revise cost (Engineering). 11.02: EGGTELSA to proceed. | Matteo Naldi |
| L00 | UNTV – Dust in CAR | ACTION | TOP | 20.02.2026 | 16.02: NCF to be issued regarding dust in CAR. | Matteo Naldi |
| L00 | AV Display – VAR 490 | ACTION | High | 27.02.2026 | 09.02: RPN to submit proposal (Concordia). SHP to revise VAR (2 displays in Bldg C). | Maximilien Montanaro |
| L00 | Press Bar / Media Center – VAR 649 / INS 524 | ACTION | High | 02.02.2026 | 23.02: RPN to issue commercial proposal. | Jessica Donatelli |
| L00 | Press Bar – INS 512 TC3-C4-2 Storage | ACTION | Medium | 20.02.2026 | 18.02: SHP to review INS. | Jean-Mathieu Ferre |
| L00 | Press Bar – Water Fountain – VAR 569 | ACTION | High | — | — | — |
| L00 | INS 512 – TC3 Storage Partition | ACTION | High | 18.02.2026 | 11.02: RPN to submit RFI if any normative issue. | Hacir Degirmencioglu |

## C2 — PRODUCTION (LB01 / LB02)

| Topic | Subject | Type | Priority | Due Date | Action Required | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| LB01 | Salle C6 – Interpretor Booth | ACTION | TOP | — | 18.02: Acoustic test to be launched as soon doors have been installed. | — |
| LB01 | Salle C6 – Chinese Donation Delivery | ACTION | High | 01.03.2026 | 14.01: RPN to schedule installation of lightings. | Jean-Mathieu Ferre |
| LB01 | Salle C6 – Stretch Ceiling in Staircase | ACTION | High | 18.02.2026 | SHP to send email to RPN confirming to go ahead with TD. SHP to issue step. | Jean-Mathieu Ferre |
| LB01 | Salle C6 – VAR 658 – Emergency Light in Staircase | ACTION | High | 11.03.2026 | 25.02: SHP to issue VAR. 09.03: APROTEC to propose new model. | Kateryna Starykova |
| LB01 | Salle C6 – F. Brunone Queries | ACTION | High | 06.03.2026 | 26.02: SHP to assess. | Cedric Kusendova |
| LB01 | BMS – RFI 1421-C / Panel TC.1.04 | ACTION | TOP | 29.10.2025 | 29.10: RPN to submit RFI 1421-D. | Matteo Naldi |
| LB02 | BMS – Functional Analysis / Wiring Diagram / Schematic | ACTION | TOP | 05.12.2025 | 07.01: RPN to resubmit the wiring diagram. | Hacir Degirmencioglu |
| LB02 | BMS – Planning | INFO | TOP | 05.12.2025 | — | Simone Conti |
| LB02 | BMS Panels – Procurement | INFO | TOP | 29.10.2025 | — | Matteo Naldi |
| LB02 | Permanent Fire Closure – INS 541 | INFO | High | 19.02.2026 | 12.02: RPN to involve SBIS in inspections. | Matteo Naldi |
| LB02 | Temporary Fire Closure – INS 545 – High Voltage Cable | ACTION | TOP | 21.01.2026 | As per Schedule 3 Chapter 17 – Business Continuity, Part 3, Paragraph 3. | Matteo Naldi |
| LB02 | INS 543 – VAR 651 – SSS Village Supply | ACTION | High | 04.02.2026 | 04.03: G&T to assess. | Clare O'Malley |
| LB02 | Archives – VAR 659 – C009.1/9.2/9.3/9.4 | ACTION | TOP | 06.03.2026 | 04.12: RPN/SHP to challenge the design. | Cedric Erard |
| LB02 | Archives LB1-LB2-LB3 – VAR 581 – Floor Finishes | ACTION | High | 14.01.2026 | 26.01: RPN to issue commercial proposal. RPN to proceed with works. | Matteo Naldi |

## C2 — PRODUCTION (S1 / LB02)

| Topic | Subject | Type | Priority | Due Date | Action Required | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| S1-LB02 | Building S1 LB02 – VAR 538 – Basement Archive Security | ACTION | TOP | 13.03.2026 | 21.01: RPN to complete works. 28.01: RPN to confirm wooden door delivery. | Jessica Donatelli |
| S1-LB02 | Building S1 LB02 – VAR 557 – Minor Security Changes | ACTION | TOP | 13.03.2026 | 18.02: RPN to comment URGENTLY. | Jessica Donatelli |
| S1-LB02 | Building S1 LB02 – VAR 660 – Bulletproof Partition | ACTION | TOP | 13.03.2026 | 04.03: SHP to raise VAR. | Jean-Mathieu Ferre |

## C3 — TESTING & COMMISSIONING

| Topic | Subject | Type | Priority | Due Date | Action Required | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| T&C | Phase 14 – Section of Work | INFO | — | — | — | — |
| T&C | FAR – Final Architectural Review | INFO | Low | — | 11.02: SHP to coordinate. | — |
| T&C | Council Chamber – F15 Panel | INFO | High | — | — | — |
| T&C | Fire Police | INFO | High | 22.10.2025 | 16.10: RPN to identify fire related tests on the board. | Simone Conti |
| T&C | Lift 5, 6, 23 | INFO | High | 22.10.2025 | 16.10: RPN to build buffer on key topics. | Simone Conti |
| T&C | OMM / PMP / Training | INFO | High | 22.10.2025 | 16.10: RPN to fix milestones & deadlines. | Simone Conti |
| T&C | PMP Submittal | ACTION | High | 09.02.2026 | 26.01: RPN to ensure 80% of PMP submitted by 09.02. | Leonardo Valentinotti |
| T&C | Training | ACTION | TOP | 09.02.2026 | 26.01: ENEOR to confirm training organisation. | Leonardo Valentinotti |
| FAR | Final Inspection – Speedup | ACTION | High | — | 21.01: RPN / SHP to speed up Final Inspection. | Leonardo Valentinotti |

## NCF – NON-CONFORMANCE FORMS

| Topic | Subject | Type | Priority | Due Date | Action Required | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| NCF 379 | Radiator – Final Inspection / Functional Test | ACTION | High | 11.02.2026 | 04.02: Final inspection and functional test to be performed as scheduled. | Leonardo Valentinotti |
| NCF 367 | Fire Enclosure – VAR 644 / INS 518 – NCF 367 | ACTION | High | 03.02.2026 | 26.01: 2 more issues on Level 1. 04.02: RPN to ensure SBIS participation. | Matteo Naldi |
| NCF 382 | Windows | ACTION | High | 03.02.2026 | 04.03: RPN to assess situation following manufacturer site visit. | Davide Cirillo |
| NCF 383 | Travertine Wall Covering | ACTION | High | 03.02.2026 | 04.03: SOMBP to raise. | Lucille Treille de Grandsaigne |

Next Meeting: 04 March 2026   |   Building C Production Meeting   |   Week 10